## Greenfield
Greenfield (deliverable & deliverable with contraints)
Site reference | Site Name | LDP2019 reference | Site Address | UPRN | Easting | Northing | Site area (ha) | Year site added | LDP/ Windfall/ Other | Planning Status | Other Detail | Planning application reference | Last planning approval date | Construction Status | Construction Start Date | Site capacity | Units to build | Plots completed in survey year | Total completions | Programmed Y1 (26-27) | Programmed Y2 (27-28) | Programmed Y3 (28-29) | Programmed Y4 (29-30) | Programmed Y5 (30-31) | Programmed Y6 (31-32) | Programmed Y7 (32-33) | Programmed Y8 (33-34) | Programmed Y9 (34-35) | Programmed Y10 (35-36) | Later Years | Total Programmed | Pipeline Timeframe | Market/ Affordable/ Mixed | Number Market | Number Affordable | No of flats | No of houses | Effective/ Constrained/ Small | Deliverability Status | Action Required | Owner | Developer | Greenfield/ Brownfield | VDL Site | Self Build | Dispute | Demolition Information
200356A | Western Gateway, South Gray Village |  | South Gray Village, Dykes of Gray Road | 009059095318 | 334131 | 731821 | 19.3417 | 2016-03-11 | Windfall | Consented (FULL) |  | 15/00121/FULM, 16/00370/FULL, 16/01012/MDPO, 17/00938/FULL, 18/00539/FULL, 24/00420/FULL, 25/00442/FULL | 2024-09-16 | Started on site | 2017-03-01 | 341 | 64 | 11 | 277 | 0 | 24 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | Short (1-3yrs) | Market | 76 | 0 | 58 | 274 | Effective | Deliverable |  | Springfield | Springfield | Greenfield | No | No
200408 | Western Gateway, West of Dykes of Gray Road |  | Swallow, Land to West of Dykes of Gray Road, Western Gateway | 009059095083 | 334038 | 731320 | 24.3312 | 2015-06-03 | Windfall | Consented (FULL) | <Null> | 14/00205/FULM, 16/01023/FULL, 17/00409/MDPO, 23/00168/FULL | 2017-07-19 | Started on site | 2015-07-20 | 230 | 41 | 10 | 189 | 0 | 0 | 14 | 14 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | Medium (4-6Yrs) | Market | 78 | 0 | 0 | 189 | Effective | Deliverable |  | Springfield | Springfield | Greenfield | No | No
200738 | Western Gateway, Liff |  | Liff Phase 2, Dykes of Gray Road | 009059103276 | 334379 | 732314 | 7.8207 | 2016-06-17 | Windfall | Consented (FULL) |  | 15/00410/FULM, 18/00992/FULL, 25/00346/FULL(35), 25/00348/FULL(42), 25/00349/FULL(23) | 2019-02-06 | Started on site | 2019-07-30 | 100 | 100 | 0 | 0 | 0 | 9 | 28 | 28 | 28 | 7 | 0 | 0 | 0 | 0 | 0 | 100 | Medium (4-6Yrs) | Market | 100 | 0 | 0 | 100 | Effective | Deliverable |  | Barratt & David Wilson, Homes North Scotland | Barratt & David Wilson, Homes North Scotland | Greenfield | No | No
201423 | Pitkerro Mill |  | Land to the West of Pitkerro Mill, Kellas Road | 009059086632 | 345078 | 733464 | 1.0007 | 2016-07-20 | Windfall | Consented (FULL) | <Null> | 16/00394/FULL | 2016-07-20 | Started on site | 2023-08-14 | 6 | 2 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Short (1-3yrs) | Market | 6 | 0 | 0 | 6 | Effective | Deliverable |  | South Tay (Dundee) Ltd | South Tay (Dundee) Ltd | Greenfield | No | No
201821 | Western Gateway, East of Dykes Of Gray Road | H42 | Land to South of West Green Park and East of Dykes Of Gray Road | 009059105901 | 334219 | 732498 | 3.2797 | 2018-04-01 | LDP | Consented (PPiP) | <Null> | 23/00617/PPPM | 2024-02-13 | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Medium (4-6Yrs) | Market | 30 | 0 | 0 | 30 | Effective | Deliverable |  | NHS Tayside | NHS Tayside | Greenfield | No | No
201822 | Western Gateway, Dykes of Gray, North East | H43 | Dykes of Gray, North East | 009059105903 | 334471 | 732016 | 13.4423 | 2018-12-17 | LDP | Consented (FULL) |  | 18/01056/FULM, 25/00184/PAN, 25/00426/FULM | 2025-11-13 | Not yet started |  | 202 | 202 | 0 | 0 | 0 | 0 | 10 | 30 | 30 | 40 | 40 | 52 | 0 | 0 | 0 | 202 | Long (7-10Yrs) | Market | 202 | 0 | 37 | 165 | Effective | Deliverable |  | Barratt & David Wilson, Homes North Scotland | Barratt & David Wilson, Homes North Scotland | Greenfield | No | No
201823 | Baldragon Farm | H44 | Land to West of St Martin Crescent and North of Adam Crescent | 009059105904 | 337401 | 734790 | 6.2216 | 2018-04-01 | LDP | Consented (FULL) |  | 19/00707/FULM | 2020-08-20 | Started on site | 2021-03-04 | 120 | 31 | 19 | 89 | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Short (1-3yrs) | Market | 50 | 0 | 0 | 120 | Effective | Deliverable |  | Avant Homes Scotland | Avant Homes Scotland | Greenfield | No | No
201824B | Ballumbie Road Phase 2 | H45 | Land to East of Ballumbie Road | 009059105905 | 344607 | 733962 | 7.4872 | 2021-05-21 | LDP | Consented (FULL) |  | 20/00423/FULM, 24/00726/FULL, 26/00006/FULL (42), 26/00007/FULL (42), 26/00008/FULL (35) | 2021-05-21 | Not yet started |  | 150 | 150 | 0 | 0 | 24 | 36 | 36 | 36 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | Medium (4-6Yrs) | Market | 150 | 0 | 0 | 150 | Effective | Deliverable |  | Persimmon Homes North Scotland | Persimmon Homes North Scotland | Greenfield | No | No
201829 | Western Gateway, Dykes of Gray, North West | H41 | Dykes of Gray, North West | 009059105898 | 333717 | 731646 | 21.9833 | 2018-01-11 | LDP | No consent |  |  |  | Not yet started |  | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 40 | 50 | 50 | 50 | 50 | 10 | 0 | 0 | 250 | Long (7-10Yrs) | Market | 250 | 0 | 0 | 250 | Effective | Deliverable |  | Springfield | Springfield | Greenfield | No | No
201830 | Linlathen | H46 | Linlathen Road, Broughty Ferry | 009059105907 | 346394 | 733242 | 15.8973 | 2018-06-25 | LDP | Consented (FULL) | <Null> | 18/00115/FULM, 19/00799/FULM, 21/00322/FULL, 21/00376/FULL, 21/00677/FULL, 21/00713/FULL | 2021-07-01 | Started on site | 2021-01-04 | 250 | 1 | 0 | 249 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Short (1-3yrs) | Market | 1 | 0 | 0 | 250 | Effective | Deliverable |  | Kirkwood Homes | Kirkwood Homes | Greenfield | No | No
[16 empty] | 1679 | 871 | 44 | 808 | 42 | 85 | 112 | 194 | 139 | 97 | 90 | 102 | 10 | 0 | 0 | 871 |  |  | 943 | 0 | 95 | 1534

## Brownfield
Brownfield (deliverable & deliverable with contraints)
Site reference | Site Name | LDP2019 reference | Site Address | UPRN | Easting | Northing | Site area (ha) | Year site added | LDP/ Windfall/ Other | Planning Status | Other Detail | Planning application reference | Last planning approval date | Construction Status | Construction Start Date | Site capacity | Units to build | Plots completed in survey year | Total completions | Programmed Y1 (26-27) | Programmed Y2 (27-28) | Programmed Y3 (28-29) | Programmed Y4 (29-30) | Programmed Y5 (30-31) | Programmed Y6 (31-32) | Programmed Y7 (32-33) | Programmed Y8 (33-34) | Programmed Y9 (34-35) | Programmed Y10 (35-36) | Later Years | Total Programmed | Pipeline Timeframe | Market/ Affordable/ Mixed | Number Market | Number Affordable | No of flats | No of houses | Effective/ Constrained/ Small | Deliverability Status | Action Required | Owner | Developer | Greenfield/ Brownfield | VDL Site | Self Build | Dispute | Demolition Information
201011 | Whitfield Primary School | H27 | Site Of Whitfield Primary School, Whitfield Drive | 009059105864 | 343218 | 733353 | 2.36 | 2023-09-13 | LDP | Consented (FULL) |  | 19/00716/FULL, 19/00776/FULL | 2023-09-13 | Started on site | 2024-08-19 | 48 | 48 | 0 | 0 | 0 | 33 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | Short (1-3yrs) | Mixed | 30 | 18 | 8 | 40 | Effective | Deliverable |  | Angus HA, George Martin Builders Ltd | Angus HA, George Martin Builders Ltd | Brownfield | Yes | No |  | 12/00550/DEMOL
202518 | Pitalpin Street |  | Land To Southeast Of Pitalpin House, Pitalpin Street | 9059103427 | 336986 | 731890 | 1.9971 | 2024-06-19 |  | Consented (FULL) |  | 23/00535/FULL | 2024-06-19 | Not yet started |  | 45 | 45 | 0 | 0 | 12 | 20 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | Short (1-3yrs) | Market | 45 | 0 | 0 | 45 | Effective | Deliverable |  | H&H Properties UK Ltd | H&H Properties UK Ltd | Brownfield |  | No
200347 | Armistead |  | 94 Monifieth Road | 009059039309 | 347412 | 731144 | 1.0067 | 2013-12-17 | Windfall | Consented (FULL) |  | 13/00642/FULL, 16/00179/FULL, 21/00904/FULL | 2022-04-15 | Started on site | 2017-06-14 | 26 | 18 | 1 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Market | 18 | 0 | 23 | 3 | Effective | Deliverable |  | H & H Properties Ltd | H & H Properties Ltd | Brownfield | No | No |  | 13/00642/FULL 15/00790/DOM1
200611 | Former Homebase Site |  | Riverside Drive | 009059078799 | 339577 | 729422 | 1.6776 | 2007-06-05 | Windfall | Consented (FULL) |  | 05/00770/FUL, 22/00463/FULL | 2007-06-05 | Started on site | 2012-04-30 | 143 | 55 | 1 | 88 | 27 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | Short (1-3yrs) | Market | 56 | 0 | 135 | 8 | Effective | Deliverable |  | H & H Properties | H & H Properties | Brownfield | No | No |  | 06/01434/DEMOL
200909 | Former Downfield Primary School | H11 | East School Road | 009059105883 | 338919 | 733132 | 1.2778 | 2009-04-01 | LDP | Consented (FULL) |  | 20/00076/FULL | 2020-11-18 | Started on site | 2023-08-23 | 23 | 14 | 9 | 9 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | Short (1-3yrs) | Market | 23 | 0 | 0 | 23 | Effective | Deliverable |  | H & H Properties | H & H Properties | Brownfield | No | No |  | 08/00848/DEMOL
200913 | Former Lawside Academy | H09 | Rannoch Road | 009059105881 | 338363 | 733094 | 4.0249 | 2009-04-01 | LDP | No consent |  |  |  | Not yet started |  | 70 | 70 | 0 | 0 | 0 | 0 | 20 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | Medium (4-6Yrs) | Market | 70 | 0 | 0 | 0 | Effective | Deliverable with contraints |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201008 | Bowling Green East | H31 | Lothian Crescent | 009059105874 | 343913 | 733373 | 1.3369 | 2010-04-01 | LDP | No consent |  |  |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Medium (4-6Yrs) | Market | 30 | 0 | 0 | 0 | Effective | Deliverable with contraints |  | Dundee City Council | Dundee City Council | Brownfield | No | No
201010 | Tranent Grove, Phase 3 | H28 | Tranent Grove | 009059105865 | 343320 | 733503 | 3.7588 | 2010-04-01 | LDP | Consented (FULL) |  | 22/00461/FULL, 24/00424/FULL | 2022-12-16 | Started on site | 2025-08-11 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 17 | 22 | 31 |  | 0 | 0 | 0 | 0 | 70 | Long (7-10Yrs) | Market | 70 | 0 | 0 | 0 | Effective | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201012 | Former Whitfield Shopping Centre | H25 | Whitfield Drive and Lothian Crescent | 009059105860 | 343056 | 733375 | 1.8274 | 2010-04-01 | LDP | No consent | Pre-application | PREAPP/041/2021, 19/00716/FULL (Part) | 2023-09-13 | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Short (1-3yrs) | Mixed | 18 | 12 | 12 | 18 | Effective | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201109 | Central Waterfront Site 6, Thomson Avenue | H17 | Central Waterfront, Thomson Avenue | 009059105906 | 340509 | 729995 | 23.9694 | 2011-04-01 | LDP | Consented (FULL) |  | 17/00113/FULM, 18/00400/FULL, 20/00399/FULL | 2020-10-16 | Started on site | 2022-10-17 | 276 | 276 | 0 | 0 | 0 | 0 | 0 | 60 | 70 | 70 | 76 | 0 | 0 | 0 | 0 | 276 | Long (7-10Yrs) | Mixed |  |  | 276 | 0 | Effective | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201110 | Former Mossgiel Primary School | H23 | Ballochmyle Drive | 009059105917 | 341769 | 732646 | 1.4577 | 2011-04-01 | LDP | Pending decision | Pre-application | PREAPP/043/2021, 22/00637/FULL |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Short (1-3yrs) | Affordable | 0 | 30 | 0 | 30 | Effective | Deliverable with contraints | Drainage solution being investigated | Abertay HA | Abertay HA | Brownfield | Yes | No
201221 | MOM Phase 4, West | H20 | Hebrides Drive, West | 009059105913 | 341048 | 733472 | 0.63833 | 2012-04-01 | LDP | No consent | Pre-application | PREAPP/078/2022 |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10+Yrs | Market | 10 | 0 | 0 | 0 | Effective | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201417 | Former Lochee Primary School | H05 | Donals Street and South Road | 009059105869 | 337330 | 731477 | 1.7818 | 2014-04-01 | LDP | Consented (FULL) |  | 22/00402/FULL | 2023-11-01 | Not yet started |  | 39 | 39 | 0 | 0 | 0 | 20 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | Short (1-3yrs) | Market | 39 | 0 | 0 | 39 | Effective | Deliverable |  | H & H Properties | H & H Properties | Brownfield | Yes | No
201510 | Lochee District Centre | H06 | Lochee District Centre, Lochee High Street | 009059105873 | 337857 | 731572 | 6.1424 | 2015-04-01 | LDP | Consented (FULL) |  | 13/00678/FULL, 15/00079/FULL, 19/00738/FULL, 22/00748/FULL | 2023-05-04 | Started on site | 2023-07-03 | 40 | 38 | 0 | 2 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | Short (1-3yrs) | Affordable | 0 | 40 | 0 | 0 | Effective | Deliverable with contraints | Drainage solution being investigated | Dundee City Council | Hillcrest HA | Brownfield | Yes | No |  | 15/00844/NDOM6
201808 | Roseangle |  | 34-36 Roseangle | 009059051397 | 339417 | 729559 | 0.1435 | 2017-12-07 |  | Consented (FULL) |  | 17/00761/FULL | 2017-12-07 | Started on site | 2023-10-30 | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | Short (1-3yrs) | Market | 7 | 0 | 7 | 0 | Effective | Deliverable |  | Formosa Developments Limited | Formosa Developments Limited | Brownfield | No | No
201813 | Former Maxwelltown Multis | H16 | Alexander Street | 009059105896 | 340172 | 731036 | 0.61367 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 30 | Medium (4-6Yrs) | Market | 30 | 0 | 0 | 0 | Effective | Deliverable with contraints | Drainage solution being investigated | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201814 | Former Gowriehill Primary School | H34 | Etive Gardens | 009059105886 | 335665 | 731239 | 1.6697 | 2018-04-01 | LDP | Pending decision |  | PREAPP/029/2022, 24/00140/PAN, 24/00366/FULL | 2024-07-16 | Not yet started |  | 35 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | Short (1-3yrs) | Affordable | 0 | 35 | 0 | 0 | Effective | Deliverable |  | Dundee City Council | Angus HA | Brownfield | Yes | No |  | 18/00051/NDOM6
201815 | Former Hillside Primary School | H35 | Denoon Terrace | 009059105887 | 336897 | 731187 | 1.9738 | 2018-04-01 | LDP | Pending decision | Pre-application | PREAPP/016/2024, 25/00134/FULL |  | Not yet started |  | 45 | 45 | 0 | 0 | 0 | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | Short (1-3yrs) | Market | 45 | 0 | 0 | 0 | Effective | Deliverable |  | Dundee City Council | H & H Properties | Brownfield | Yes | No |  | 18/00050/NDOM6
201816 | Former St Mary's Infant School | H36 | Former St Mary's Infant School, High Street, Lochee | 009059105889 | 337998 | 731337 | 0.36187 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Short (1-3yrs) | Affordable | 0 | 10 | 0 | 0 | Effective | Deliverable with contraints | Draingage solution being investigated | Dundee City Council | Hillcrest HA | Brownfield | Yes | No |  | 17/00228/NDOM6
201817 | Former Baldragon Academy | H37 | Burn Street | 009059105890 | 339111 | 733973 | 4.926 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 70 | 70 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | Medium (4-6Yrs) | Affordable | 0 | 70 | 0 | 0 | Effective | Deliverable | Marketing of site for housing | Dundee City Council | Abertay HA | Brownfield | No | No
201825 | Former Railyards | H14 | Greenmarket | 009059105888 | 339467 | 729510 | 2.1768 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 110 | 110 | 0 | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | Medium (4-6Yrs) | Market | 110 | 0 | 0 | 0 | Effective | Deliverable with contraints |  | Scottish Enterprise |  | Brownfield | Yes | No
201826C | Summerfield Gardens | H29 | Land to West Of Summerfield Avenue at Summerfield Gardens | 009059105870 | 343614 | 733089 | 1.9422 | 2022-06-13 | LDP | Consented (FULL) |  | 21/00736/FULL | 2022-06-13 | Started on site | 2024-03-12 | 34 | 17 | 11 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Short (1-3yrs) | Market | 28 | 0 | 0 | 34 | Effective | Deliverable |  | Invertay Homes Ltd | Invertay Homes Ltd | Brownfield | Yes | No
201827 | Kellyfield | H33 | Drumgeith Road | 009059105878 | 344237 | 733239 | 8.4241 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 100 | Medium (4-6Yrs) | Market | 100 | 0 | 0 | 0 | Effective | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201912 | Ellengowan Drive |  | South Of Arbroath Road, West Of Dalkeith Road, Ellengowan Rd | 009059104967 | 341769 | 731105 | 3.9484 | 2019-04-09 | Windfall | Consented (FULL) |  | 18/00487/FULM | 2019-04-09 | Started on site | 2020-08-28 | 129 | 59 | 0 | 70 | 0 | 24 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | Short (1-3yrs) | Affordable | 0 | 60 | 72 | 57 | Effective | Deliverable |  |  | Hillcrest HA | Brownfield | No | No |  | 18/00752/DOM1, 18/00753/DOM1, 24/00123/DOM4
202012 | Former Stewart House |  | Land at Former Stewart House, Kingsway East | 009059106080 | 342852 | 731829 | 2.8817 | 2019-12-18 | Windfall | Consented (FULL) |  | 19/00687/FULM, 23/00449/FULL | 2023-09-07 | Started on site | 2023-07-24 | 71 | 14 | 34 | 57 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | Short (1-3yrs) | Market | 48 | 0 | 0 | 71 | Effective | Deliverable |  | Persimmon Homes North Scotland | Persimmon Homes North Scotland | Brownfield | No | No |  | 17/00183/NDOM7
202024 | Land to North of Pitkerro Road |  | Land to North of Pitkerro Road and East of Longhaugh Road | 009059094469 | 342795 | 732954 | 1.02 | 2020-05-21 | Windfall | Consented (FULL) |  | 19/00063/FULL | 2020-05-21 | Started on site | 2021-08-02 | 14 | 2 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Short (1-3yrs) | Market | 2 | 0 | 0 | 14 | Effective | Deliverable |  | Longhaugh Developments Ltd | Longhaugh Developments Ltd | Brownfield | No | No
202030 | Gellatly Street |  | 3 Gellatly Street | 009059018953 | 340610 | 730351 | 0.12902 | 2020-07-30 | Windfall | Consented (FULL) |  | 19/00502/FULL, 21/00215/FULL | 2021-12-07 | Started on site | 2023-03-01 | 49 | 49 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | Short (1-3yrs) | Market | 49 | 0 | 49 | 0 | Effective | Deliverable |  | McGill (Dock Street) Ltd | McGill (Dock Street) Ltd | Brownfield | No | No
202061B | Dalkeith Road |  | 69 Dalkeith Road | 009059066413 | 341712 | 731577 | 0.22415 | 2020-10-22 | Windfall | Consented (FULL) |  | 20/00142/FULL | 2020-10-22 | Started on site | 2021-09-29 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 4 | 0 | 3 | 1 | Effective | Deliverable with contraints | Ownership | Marvend Ltd | Marvend Ltd | Brownfield | No | No
202065 | Former Tennis Club |  | 57 Dalkeith Road | 009059035680 | 341769 | 731399 | 0.26635 | 2020-11-18 | Windfall | Consented (FULL) |  | 20/00209/FULL | 2020-11-18 | Started on site | 2024-05-01 | 8 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 8 | 0 | 0 | 8 | Effective | Deliverable |  | H & H Properties UK Ltd | H & H Properties UK Ltd | Brownfield | No | No
202104 | Former Rosebank Primary School |  | Land at Rosebank Road | 009059107104 | 339990 | 730905 | 1.3421 | 2021-06-16 | Windfall | Consented (FULL) |  | 21/00011/FULL | 2021-06-16 | Started on site | 2022-06-10 | 40 | 24 | 3 | 16 | 13 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | Short (1-3yrs) | Market | 27 | 0 | 0 | 40 | Effective | Deliverable |  | Discovery Homes (Dundee) Ltd | Discovery Homes (Dundee) Ltd | Brownfield | No | No
202108 | Former Tay Rope Works |  | Land at Former Tay Rope Works, Magdalen Yard Road | 009059078253 | 339151 | 729525 | 0.25114 | 2021-04-21 | Windfall | Consented (FULL) |  | 19/00297/FULL | 2021-04-21 | Started on site | 2023-03-27 | 9 | 4 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 9 | 0 | 4 | 5 | Effective | Deliverable |  | F & H Property | F & H Property | Brownfield | No | No
202115 | Whitehall Crescent |  | 3 Whitehall Crescent | 009059059845 | 340357 | 730131 | 0.028412 | 2021-11-18 | Windfall | Consented (FULL) |  | 21/00636/FULL | 2021-11-18 | Started on site | 2024-06-01 | 14 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | Short (1-3yrs) | Market | 14 | 0 | 14 | 0 | Effective | Deliverable |  | Joup Property Ltd | Joup Property Ltd | Brownfield | No | No
202201 | Blackness Road |  | Land to East of 247 Blackness Road | 009059111353 | 338564 | 730306 | 0.17708 | 2022-02-09 | Windfall | Consented (FULL) |  | 21/00525/FULL, 25/00063/FULL | 2025-04-09 | Started on site | 2025-08-18 | 24 | 24 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | Short (1-3yrs) | Affordable | 0 | 0 | 24 | 0 | Effective | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | No | No
202204 | Site of James Keiller Buildings |  | 32 - 34 Mains Loan | 009059076133 | 340952 | 732266 | 6.3045 | 2022-02-17 | Windfall | Consented (FULL) |  | 20/00098/FULM, 22/00627/FULL | 2024-01-19 | Started on site | 2022-11-15 | 223 | 60 | 73 | 163 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | Short (1-3yrs) | Market | 133 | 0 | 56 | 167 | Effective | Deliverable |  | Marketgait Developments | Barratt & David Wilson Homes North Scotland | Brownfield | No | No |  | 07/00233/DEMOL
202205 | Burnside Street |  | 55 Burnside Street | 009059078219 | 338192 | 731432 | 0.57137 | 2022-03-17 | Windfall | Consented (FULL) |  | 21/00857/FULM | 2022-03-17 | Started on site | 2024-08-19 | 54 | 54 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | Short (1-3yrs) | Affordable | 0 | 54 | 54 | 0 | Effective | Deliverable |  | Hillcrest HA | George Martin Builders | Brownfield | Yes | No
202308 | Mains of Balgay |  | Vacant Workshop and Store, Mains Of Balgay, Elliot Road | 009059075236 | 337381 | 730420 | 0.30628 | 2022-12-22 | Windfall | Consented (FULL) |  | 22/00563/FULL | 2022-12-22 | Started on site | 2024-03-04 | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Short (1-3yrs) | Market | 5 | 0 | 0 | 5 | Effective | Deliverable |  | Private | Private | Brownfield | No | No |  | 23/00141/DOM1
202319 | Donalds Lane |  | Site Of Former 6 Donalds Lane | 009059105499 | 336880 | 731887 | 0.21219 | 2023-08-10 | Windfall | Consented (FULL) |  | 22/00376/FULL | 2023-08-10 | Not yet started |  | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 4 | 0 | 0 | 4 | Effective | Deliverable |  | H & H Properties UK Ltd | H & H Properties UK Ltd | Brownfield | Yes | No
202322 | The High Kirk |  | The High Kirk, 119A Kinghorne Road | 009059086980 | 339491 | 731290 | 0.2027 | 2023-10-12 | Windfall | Consented (FULL) |  | 23/00389/FULL | 2023-10-12 | Started on site | 2024-08-14 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 8 | 0 | Effective | Deliverable |  | David Gray Construction Ltd | David Gray Construction Ltd | Brownfield | No | No |  | Demolition of ancillary hall building
202324 | The Rock |  | Land At Dickson Avenue | 009059113097 | 336124 | 731003 | 0.15234 | 2023-11-07 | Windfall | Consented (FULL) |  | 23/00510/FULL | 2023-11-07 | Not yet started |  | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | Short (1-3yrs) | Market | 16 | 0 | 16 | 0 | Effective | Deliverable |  | Rock Developments (Scotland) Ltd | Rock Developments (Scotland) Ltd | Brownfield | No | No
202328 | Dens Road |  | Eagle Mills, 1 Dens Road | 009059046025 | 340788 | 731048 | 0.33086 | 2023-04-24 |  | Consented (FULL) |  | 22/00077/FULL, 26/00046/S42 pending | 2023-04-24 | Not yet started |  | 34 | 34 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | Short (1-3yrs) | Market | 34 | 0 | 34 | 0 | Effective | Deliverable |  | Eagle Mill Capital Ltd | Eagle Mill Capital Ltd | Brownfield | No | No
202401 | Caird Rest |  | Caird Rest, 172 Nethergate | 009059088053 | 339852 | 729813 | 0.2397 | 2024-01-10 | Windfall | Consented (FULL) |  | 23/00451/FULL | 2024-01-10 | Not yet started |  | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Short (1-3yrs) | Market | 5 | 0 | 5 | 0 | Effective | Deliverable |  | Private | Private | Brownfield | No | No
202408 | East Port House |  | East Port House, 65 - 67 King Street | 009059082339 | 340679 | 730777 | 0.069167 | 2024-04-08 | Windfall | Consented (FULL) |  | 24/00196/FULL | 2024-09-20 | Not yet started |  | 18 | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Market | 18 | 0 | 18 | 0 | Effective | Deliverable |  | Marketgait Developments Ltd | Marketgait Developments Ltd | Brownfield | No | No
202411 | Former Hilltown Market |  | Site Of Former Hilltown Market, Main Street | 009059107737 | 340125 | 731525 | 1.6349 | 2024-05-30 | Windfall | Consented (FULL) |  | 23/00208/FULM, 25/0040/NMV | 2024-05-30 | Not yet started |  | 131 | 131 | 0 | 0 | 31 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | Short (1-3yrs) | Affordable | 0 | 131 | 122 | 9 | Effective | Deliverable |  | Springfield Partnerships | Springfield Partnerships Hillcrest HA | Brownfield | Yes | No |  | 18/00677/NDOM7
202414 | Ferry House Residential Home |  | Ferry House Residential Home, 8 Gray Street, Broughty Ferry | 009059049402 | 346265 | 730684 | 0.062191 | 2024-07-05 | Windfall | Consented (FULL) |  | 24/00453/FULL | 2025-02-28 | Not yet started |  | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | Short (1-3yrs) | Affordable | 0 | 7 | 7 | 0 | Effective | Deliverable |  | Hillcrest HA | Hillcrest HA | Brownfield | No | No
202419 | Sangobeg House |  | Sangobeg House, 4 Francis Street | 009059017575 | 339571 | 731966 | 0.14222 | 2024-08-20 | Windfall | Consented (FULL) |  | 24/00530/FULL | 2025-01-17 | Started on site | 2026-01-05 | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | Short (1-3yrs) | Market | 9 | 0 | 0 | 0 | Effective | Deliverable |  | Sangobeg Developments Ltd | Sangobeg Developments Ltd | Brownfield | No | No
202424 | Angus Street, Lochee |  | Former Community Centre, Angus Street, Lochee | 009059113219 | 337561 | 731866 | 0.33905 | 2024-11-04 | Windfall | Consented (FULL) |  | 24/00703/FULL | 2025-03-12 | Started on site | 2025-08-18 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Affordable | 0 | 8 | 0 | 8 | Effective | Deliverable |  | Abertay Housing Association | Abertay Housing Association | Brownfield | No | No
202426 | Commercial Street |  | 9 - 17 Commercial Street | 009059069855 | 340546 | 730299 | 0.031011 | 2024-12-10 | Windfall | Consented (FULL) |  | 24/00752/FULL | 2025-03-28 | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 4 | 0 | 4 | 0 | Effective | Deliverable |  | Sovereign Properties Stafford Ltd | Sovereign Properties Stafford Ltd | Brownfield | No | No
202503 | Trades Lane |  | 28 Trades Lane | 009059076129 | 340689 | 730402 | 0.080693 | 2023-06-02 | Windfall | Consented (FULL) |  | 18/00988/FULL, 23/00172/FULL | 2023-06-02 | Not yet started |  | 28 | 28 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | Short (1-3yrs) | Market | 28 | 0 | 28 | 0 | Effective | Deliverable |  |  |  | Brownfield | No | No |  | 24/00496/NDOM7
202513 | Perth Road |  | Fernbrae Hospital, 329 Perth Road | 009059085246 | 337615 | 729923 | 1.1481 | 2025-11-27 | Windfall | Consented (FULL) |  | 25/00437/FULL | 2025-11-27 | Not yet started |  | 25 | 25 | 0 | 0 | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | Short (1-3yrs) | Market | 25 | 0 | 20 | 5 | Effective | Deliverable |  | Kirkwood Homes | Kirkwood Homes | Brownfield | No | No
202601 | Drumgeith Road |  | Montpelier Smithy House, Drumgeith Road | 009059031313 | 344640 | 733295 | 0.26142 | 2026-01-26 | Windfall | Consented (PPiP) |  | 25/00494/PPPL | 2026-01-26 | Not yet started |  | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | Short (1-3yrs) | Market | 7 | 0 | 0 | 7 | Effective | Deliverable |  |  |  | Brownfield | No | No
Totals | [15 empty] | 2269 | 1818 | 141 | 451 | 306 | 536 | 315 | 237 | 182 | 156 | 76 | 0 | 0 | 0 | 10 | 1818 |  |  | 1186 | 475 | 999 | 641

## Small Sites
Small sites
Site reference | Site Name | LDP2019 reference | Site Address | UPRN | Easting | Northing | Site area (ha) | Year site added | LDP/ Windfall/ Other | Planning Status | Other Detail | Planning application reference | Last planning approval date | Construction Status | Construction Start Date | Site capacity | Units to build | Plots completed in survey year | Total completions | Pipeline Timeframe | Market/ Affordable/ Mixed | Number Market | Number Affordable | No of flats | No of houses | Effective/ Constrained/ Small | Deliverability Status | Action Required | Owner | Developer | Greenfield/ Brownfield | VDL Site | Self Build | Dispute | Demolition Information
201607L | Collingwood Crescent |  | Land to West of 20 Collingwood Crescent, Broughty Ferry | 009059103958 | 347875 | 731329 | 0.040366 | 2015-05-15 | Windfall | Consented (FULL) | <Null> | 15/00138/FULL, 19/00031/FULL | 2019-05-01 | Started on site | 2021-09-10 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
201705 | Dalkeith Road |  | 68 Dalkeith Road | 009059019101 | 341641 | 731598 | 0.14295 | 2016-07-25 |  | Consented (FULL) |  | 16/00310/FULL | 2016-07-25 | Started on site | 2020-12-14 | 2 | 1 | 0 | 1 |  |  |  |  | 2 | 0 | Small | Deliverable
201705H | Monifieth Road |  | Garden Ground to South of 96 Monifieth Road | 009059104956 | 347449 | 731179 | 0.057013 | 2016-09-14 | Windfall | Consented (FULL) |  | 16/00505/FULL | 2016-09-14 | Started on site | 2018-01-22 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
201705K | Holly Hill |  | Holly Hill, 69 Dundee Road, Broughty Ferry | 009059084670 | 344419 | 731195 | 0.18299 | 2016-12-08 | Windfall | Consented (FULL) |  | 16/00832/FULL, 19/00845/FULL, 22/00651/FULL, 25/00467/FULL | 2022-11-24 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
201805B | Monifieth Road |  | 92A Monifieth Road, Broughty Ferry | 009059036721 | 347338 | 731179 | 0.10675 | 2017-05-12 | Windfall | Consented (FULL) |  | 16/00745/FULL | 2017-05-12 | Started on site | 2022-01-13 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Small | Deliverable |  | Private | Private | Brownfield | No | No
201805J | Princes Street |  | 161 Princes Street | 009059095865 | 341072 | 730954 | 0.038506 | 2017-11-15 | Windfall | Consented (FULL) |  | 17/00769/FULL | 2017-11-15 | Started on site | 2019-01-21 | 3 | 3 | 0 | 0 | Short (1-3yrs) | Market | 3 | 0 | 3 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202004P | Rockfield Crescent |  | Garden Ground to North of 7 Rockfield Crescent | 009059107739 | 338252 | 730123 | 0.051985 | 2020-01-31 | Windfall | Consented (PPiP) |  | 19/00914/PPPL, 23/00511/PPPL | 2023-09-29 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202019D | Stonelee Guest House |  | Stonelee Guest House, 69 Monifieth Road, Broughty Ferry | 009059006118 | 346866 | 731047 | 0.021311 | 2020-05-26 | Windfall | Consented (FULL) |  | 20/00148/FULL | 2020-05-26 | Started on site | 2021-10-11 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202031 | Pitkerro Mill |  | Pitkerro Mill, Kellas Road | 009059086633 | 345088 | 733487 | 0.21123 | 2020-07-31 | Windfall | Consented (FULL) |  | 19/00861/FULL, 23/00238/FULL, 23/00319/FULL | 2023-08-02 | Started on site | 2023-08-14 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Small | Deliverable |  | Harbyn Properties | Harbyn Properties | Brownfield | No | No
202032A | Symers Street |  | Land to the East of 6, Symers Street | 009059107098 | 338543 | 734031 | 0.025906 | 2020-07-31 | Windfall | Consented (FULL) |  | 20/00232/FULL, 23/00474/FULL | 2023-09-29 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202035A | Bowling Green |  | Land to West of Bowling Green, Adelaide Place | 009059108128 | 339508 | 731113 | 0.049833 | 2020-09-04 | Windfall | Consented (FULL) |  | 20/00310/PPPL, 23/00314/FULL | 2023-08-28 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202035C | Albany Road |  | Garden Ground to South of 50 Albany Road, Broughty Ferry | 009059108124 | 344782 | 731333 | 0.13039 | 2020-10-02 | Windfall | Consented (PPiP) |  | 20/00289/PPPL, 23/00839/PPPL | 2024-02-02 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202035D | Springhill |  | 13 Springhill | 009059076547 | 341571 | 731090 | 0.047011 | 2020-11-10 | Windfall | Consented (FULL) |  | 20/00459/FULL | 2020-11-10 | Started on site | 2021-01-01 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202035F | Dudhope Terrace |  | 9 Dudhope Terrace | 009059065182 | 339435 | 730892 | 0.13097 | 2020-11-12 | Windfall | Consented (FULL) |  | 20/00548/FULL | 2020-11-12 | Started on site | 2021-05-09 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202035G | Victoria Chambers |  | G/1 Office, Victoria Chambers, 10 Victoria Road | 009059075915 | 340214 | 730670 | 0.010618 | 2020-11-26 | Windfall | Consented (FULL) |  | 20/00133/FULL | 2020-11-26 | Started on site | 2021-12-13 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Tayside Property Management | Tayside Property Management | Brownfield | No | Single plot
202035H | Murraygate |  | 1/0, 39 Murraygate | 009059087550 | 340421 | 730459 | 0.018125 | 2020-12-11 | Windfall | Consented (FULL) |  | 20/00509/FULL | 2020-12-11 | Started on site | 2022-05-27 | 3 | 3 | 0 | 0 | Short (1-3yrs) | Market | 3 | 0 | 3 | 0 | Small | Deliverable |  | Casa Fresa Holdings LLP | Casa Fresa Holdings LLP | Brownfield | No | No
202043 | Brown Street |  | Land to South of 75/77 Brown Street, Broughty Ferry | 009059108220 | 346017 | 730834 | 0.012892 | 2020-11-06 | Windfall | Consented (FULL) |  | 20/00529/PPPL, 22/00547/FULL | 2022-11-18 | Started on site | 2025-02-17 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 2 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202105C | Frederick Street |  | Garden Ground at 45 Frederick Street | 009059110659 | 338778 | 733449 | 0.072435 | 2021-08-01 | Windfall | Consented (FULL) |  | 20/00721/FULL, 22/00756/FULL | 2023-02-08 | Started on site | 2024-07-23 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202105I | Strathern Road |  | 140 Strathern Road, Broughty Ferry | 009059070792 | 345677 | 731472 | 0.11464 | 2021-08-01 | Windfall | Consented (FULL) |  | 20/00798/FULL | 2021-08-20 | Started on site | 2024-08-16 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot |  | 20/00798/FULL
202116 | Lammerton Terrace |  | Garden Ground To North Of 3A Lammerton Terrace | 009059110892 | 341342 | 732274 | 0.039653 | 2021-07-05 |  | Consented (FULL) |  | 21/00077/FULL | 2021-07-05 | Started on site | 2024-03-06 | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202208 | Forthill Road |  | 10 Forthill Road, Broughty Ferry | 009059013261 | 346229 | 731308 | 0.041527 | 2022-03-16 | Windfall | Consented (PPiP) |  | 21/00688/PPPL | 2022-03-16 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202302 | Ellislea Road |  | Garden Ground at 9 Ellislea Road, Broughty Ferry | 009059111889 | 345024 | 731414 | 0.10892 | 2022-08-23 | Windfall | Consented (FULL) |  | 22/00373/FULL | 2022-08-23 | Started on site | 2023-12-05 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202304 | Camphill Road |  | Land South of 65 Camphill Road, Broughty Ferry | 009059112325 | 346894 | 731323 | 0.17794 | 2022-11-10 | Windfall | Consented (FULL) |  | 22/00545/FULL, 25/00602/S42 (time extension) | 2025-12-18 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202306 | Lauderdale Avenue |  | Garden Ground to South of 88 Lauderdale Avenue | 009059112552 | 338288 | 733486 | 0.03012 | 2022-11-25 | Windfall | Consented (PPiP) |  | 22/00535/PPPL | 2022-11-25 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202314 | Daniel Terrace |  | 2 Daniel Terrace | 009059082171 | 339440 | 730204 | 0.033733 | 2023-05-18 | Windfall | Consented (FULL) |  | 23/00112/FULL | 2023-05-18 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 2 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202315 | Broughty Ferry Road |  | 208 Broughty Ferry Road | 009059017913 | 342298 | 731118 | 0.11554 | 2023-05-19 | Windfall | Consented (FULL) |  | 23/00128/FULL | 2023-05-19 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202316 | Strathern Road |  | 32 Strathern Road, Broughty Ferry | 009059112851 | 344271 | 731367 | 0.085898 | 2023-07-21 | Windfall | Consented (FULL) |  | 23/00199/FULL | 2023-07-21 | Started on site | 2024-04-19 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202317 | Cleghorn Street |  | 25A Cleghorn Street | 009059010503 | 338740 | 730664 | 0.0040554 | 2023-07-28 | Windfall | Consented (FULL) |  | 23/00279/FULL | 2023-07-28 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202318 | India Buildings |  | Upper Ground Floor, India Buildings, 86 Bell Street | 009059000446 | 340211 | 730614 | 0.0077227 | 2023-07-31 | Windfall | Consented (FULL) |  | 23/00345/FULL | 2023-07-31 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Pavillion Properties | Pavillion Properties | Brownfield | No | Single plot
202321 | Kingsway |  | Garden Ground, 74 Kingsway | 009059042327 | 340809 | 732504 | 0.031726 | 2023-08-10 | Windfall | Consented (PPiP) |  | 23/00110/PPPL, 24/00342/APCONL | 2024-07-23 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202323 | Nethergate |  | 32 Nethergate | 009059030567 | 340252 | 730132 | 0.012693 | 2023-11-03 | Windfall | Consented (FULL) |  | 23/00587/FULL | 2023-11-03 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 2 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202326 | India Buildings |  | Unit 2, India Buildings, 86 Bell Street | 009059001075 | 340204 | 730611 | 0.017497 | 2023-12-21 | Windfall | Consented (FULL) |  | 23/00694/FULL | 2023-12-21 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Pavillion Properties | Pavillion Properties | Brownfield | No | Single plot
202402 | Bell Street |  | 46·& 50 Bell Street | 009059077214 | 340141 | 730567 | 0.011603 | 2024-01-12 | Windfall | Consented (FULL) |  | 23/00701/FULL | 2024-01-12 | Started on site | 2025-06-01 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202403 | Stephens Yard |  | Land South Of Stephens Yard, Shepherds Loan | 009059079444 | 338788 | 729671 | 0.050142 | 2024-01-23 | Windfall | Consented (FULL) |  | 23/00170/FULL | 2024-01-23 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 2 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202404 | Perth Road |  | Garden Ground East Of 381 Perth Road | 009059113110 | 336752 | 730030 | 0.31689 | 2024-02-05 | Windfall | Consented (FULL) |  | 23/00668/FULL | 2024-02-05 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202405 | India Buildings |  | Unit 1, India Buildings, 86 Bell Street | 009059001074 | 340205 | 730599 | 0.012526 | 2024-02-29 | Windfall | Consented (FULL) |  | 23/00855/FULL | 2024-02-29 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202406 | Gotterstone Drive |  | Land East Of 61 Gotterstone Drive | 009059068873 | 344544 | 731906 | 0.035516 | 2024-03-15 | Windfall | Consented (FULL) |  | 23/00079/FULL | 2024-03-15 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202407 | Woodcroft |  | Land To West Of Woodcroft, Dundee Road, Broughty Ferry | 009059096087 | 344360 | 731160 | 0.13338 | 2024-03-20 | Windfall | Consented (FULL) |  | 23/00404/FULL | 2024-03-20 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Greenfield | No | Single plot
202409 | Liff Road |  | 52 Liff Road | 009059036633 | 337542 | 731818 | 0.0034755 | 2024-04-09 | Windfall | Consented (FULL) |  | 24/00239/FULL | 2024-06-26 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202410 | Hillbank Road |  | 1 Hillbank Road | 009059010058 | 340583 | 731366 | 0.043539 | 2024-04-17 | Windfall | Consented (FULL) |  | 24/00103/FULL | 2024-04-17 | Started on site | 2025-09-15 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Affordable | 0 | 2 | 2 | 0 | Small | Deliverable |  | Hillcrest Homes (Scotland) Ltd |  | Brownfield | No | No
202413 | King Street |  | 421 King Street, Broughty Ferry | 009059047674 | 346578 | 730656 | 0.036566 | 2024-06-21 | Windfall | Consented (FULL) |  | 24/00427/FULL | 2024-09-04 | Started on site | 2026-03-04 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot |  | 24/00428/CON, 24/00511/DOM4
202422 | Belsize House |  | Belsize House, Belsize Road | 009059010481 | 344010 | 731255 | 0.21587 | 2024-09-19 | Windfall | Consented (FULL) |  | 24/00560/FULL | 2024-12-04 | Started on site | 2025-05-07 | 3 | 3 | 0 | 0 | Short (1-3yrs) | Market | 3 | 0 | 0 | 3 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202429 | Myrekirk Road |  | Garden Ground North Of 5 Myrekirk Road | 009059113900 | 335459 | 731606 | 0.045775 | 2024-12-11 | Windfall | Consented (FULL) |  | 24/00777/FULL | 2025-02-06 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202430 | Scrimgeours Building |  | 4/1 Scrimgeours Building, 4 Whitehall Street | 009059075161 | 340278 | 730164 | 0.0074745 | 2024-12-18 | Windfall | Consented (FULL) |  | 24/00804/FULL | 2025-03-10 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202501 | Arbroath Road |  | 105 Arbroath Road | 009059070070 | 341561 | 731147 | 0.012721 | 2025-01-23 | Windfall | Consented (FULL) |  | 22/00696/FULL, 24/00788/FULL | 2025-03-13 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Deliverable |  | Alex Sikorsky AK Property Ltd | Alex Sikorsky AK Property Ltd | Brownfield | No | No
202502 | Clovis Duveau Drive |  | Land To East Of 15 Clovis Duveau Drive | 009059103617 | 335515 | 730237 | 0.051964 | 2025-01-30 | Windfall | Consented (FULL) |  | 21/00423/FULL, 24/00053/FULL, 24/00802/FULL | 2024-05-27 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202505 | Gray Street |  | Harbour Cottage, 1A Gray Street, Broughty Ferry | 009059069450 | 346229 | 730659 | 0.0055303 | 2025-05-09 | Windfall | Consented (FULL) |  | 25/00129/FULL | 2025-05-09 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202506 | Broughty Ferry Court |  | Land At Broughty Ferry Court, Baldovie Road | 009059089111 | 345236 | 732413 | 0.10683 | 2025-06-27 | Windfall | Consented (PPiP) |  | 25/00205/PPPL | 2025-06-27 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202507 | Commercial Street |  | 1/2, 45 Commercial Street | 009059067568 | 340466 | 730345 | 0.045582 | 2025-08-19 | Windfall | Consented (FULL) |  | 25/00240/FULL | 2025-08-19 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202508 | Commercial Street |  | 9 - 17 Commercial Street | 009059069855 | 340552 | 730296 | 0.016179 | 2025-10-03 | Windfall | Consented (FULL) |  | 25/00384/FULL | 2025-10-03 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 1 | 0 | Small | Deliverable |  | Sovereign Properties Stafford Ltd | Sovereign Properties Stafford Ltd | Brownfield | No | No
202509 | Perth Road |  | Land at 381 Perth Road | 009059114482 | 336736 | 729949 | 0.073402 | 2025-10-08 | Windfall | Consented (FULL) |  | 25/00360/FULL | 2025-10-08 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | No
202510 | Balgowan Drive |  | Land At 7 Balgowan Drive | 009059113623 | 339134 | 733842 | 0.05606 | 2025-11-03 | Windfall | Consented (FULL) |  | 25/00203/FULL | 2025-11-03 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | No |  | 19/00536/DOM4
202511 | Belsize Road |  | Belsize House, Belsize Road | 009059010481 | 343994 | 731284 | 0.10556 | 2025-11-06 | Windfall | Consented (FULL) |  | 25/00425/FULL | 2025-11-06 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202512 | Avon Place |  | 12 Avon Place, Broughty Ferry | 009059061404 | 348058 | 732850 | 0.013434 | 2025-11-07 | Windfall | Consented (FULL) |  | 25/00501/FULL | 2025-11-07 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202514 | Whitfield Drive |  | Sun City Demonstration House, Whitfield Drive | 009059046042 | 343235 | 733264 | 0.063131 | 2025-12-11 |  | Consented (FULL) |  | 25/00513/FULL | 2025-12-11 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | George Martin Builders | George Martin Builders | Brownfield | No | No
202515 | Douglas Terrace |  | 20 Douglas Terrace, Broughty Ferry | 009059084664 | 345451 | 731089 | 0.04819 | 2025-12-18 |  | Consented (FULL) |  | 25/00618/FULL | 2025-12-18 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202602 | Tay Street Lane |  | 17 - 19 Tay Street Lane | 009059093703 | 339984 | 730005 | 0.0066702 | 2026-02-02 | Windfall | Consented (FULL) |  | 25/00621/FULL | 2026-02-02 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 1 | 0 | Small | Deliverable |  | Private | Private | Brownfield | No | Single plot
202603 | Albany Road |  | 22 Albany Road, Broughty Ferry | 009059000526 | 344390 | 731259 | 0.14105 | 2026-03-18 |  | Consented (FULL) |  | 25/00675/APCONL | 2026-03-18 | Not yet started |  | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 1 | Small | Deliverable |  | Private | Private | Brownfield
[16 empty] | 73 | 72 | 0 | 1 |  |  | 55 | 2

## Constrained
Constrained
Site reference | Site Name | LDP2019 reference | Site Address | UPRN | Easting | Northing | Site area (ha) | Year site added | LDP/ Windfall/ Other | Planning Status | Other Detail | Planning application reference | Last planning approval date | Construction Status | Construction Start Date | Site capacity | Units to build | Plots completed in survey year | Total completions | Programmed Y1 | Programmed Y2 | Programmed Y3 | Programmed Y4 | Programmed Y5 | Programmed Y6 | Programmed Y7 | Programmed Y8 | Programmed Y9 | Programmed Y10 | Later Years | Total Programmed | Pipeline Timeframe | Market/ Affordable/ Mixed | Number Market | Number Affordable | No of flats | No of houses | Effective/ Constrained/ Small | Deliverability Status | Action Required | Owner | Developer | Greenfield/ Brownfield | VDL Site | Self Build | Dispute | Demolition Information
200321 | Queen Victoria Works | H13 | Brook Street, Dundee | 009059105885 | 339248 | 730423 | 1.2498 | 2003-04-01 | LDP | No consent |  |  |  | Not yet started |  | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10+Yrs | Market | 50 | 0 | 0 | 50 | Constrained | Constrained |  | Private | Private | Brownfield | Yes | No
200353 | Lothian Crescent | H26 | Lothian Crescent | 009059105862 | 343118 | 733510 | 0.83453 | 2003-04-01 | LDP | No consent | <Null> |  |  | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | 0 | 15 | 0 | 0 | Constrained | Constrained |  |  |  | Brownfield | Yes | No
200728 | Princes Street | H18 | Princes Street | 009059105909 | 340941 | 730852 | 0.25972 | 2007-04-01 | LDP | No consent | Pre-application | PREAPP/001/2019 |  | Not yet started |  | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10+Yrs | Market | 20 | 0 | 0 | 0 | Constrained | Constrained |  | Dundee City Council |  | Brownfield | No | No
200807 | Quarry Gardens | H04 | Land at Quarry Gardens | 009059105867 | 337130 | 732089 | 0.44319 | 2008-04-01 | LDP | No consent | <Null> |  |  | Not yet started |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 18 | 0 | 0 | 0 | Constrained | Constrained |  |  |  | Brownfield | Yes | No
201102 | Dura Street |  | 3 Dura Street | 009059018817 | 340858 | 731298 | 0.07577 | 2010-12-21 | Windfall | Consented (FULL) |  | 10/00676/FULL, 13/00824/FULL, 17/00014/FULL, 20/00018/FULL, 23/00153/FULL | 2023-06-29 | Not yet started |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Medium (4-6Yrs) | Market | 8 | 0 | 8 | 0 | Constrained | Deliverable with contraints | Ownership | B & L Whittet Ltd |  | Brownfield | No | No |  | existing car sales & MOT garage
201205 | Earn Crescent | H02 | Land at Earn Crescent | 009059105859 | 336292 | 730903 | 0.56489 | 2012-04-01 | LDP | No consent | <Null> |  |  | Not yet started |  | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10+Yrs | Market | 20 | 0 | 0 | 0 | Constrained | Constrained |  | Dundee City Council |  | Brownfield | No | No
201220 | MOM Phase 4 | H19 | Land at Barns Of Claverhouse Road | 009059105911 | 340911 | 733631 | 0.41142 | 2012-04-01 | LDP | No consent | <Null> |  |  | Not yet started |  | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 12 | 0 | 0 | 0 | Constrained | Constrained |  |  |  | Brownfield | No | No
201413 | Clatto Reservoir | H03 | Land To South Of Clatto Reservoir, Dalmahoy Drive | 009059105861 | 336967 | 734365 | 3.4021 | 2014-04-01 | LDP | No consent | <Null> |  |  | Not yet started |  | 60 | 60 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | Medium (4-6Yrs) | Market | 60 | 0 | 0 | 0 | Constrained | Constrained |  | Scottish Water |  | Brownfield | No | No
201424 | Strathyre Avenue | H47 | Land To East Of Strathyre Avenue, Broughty Ferry | 009059105908 | 347040 | 732767 | 1.5713 | 2014-04-01 | LDP | No consent | <Null> |  |  | Not yet started |  | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 26 | 0 | 0 | 0 | Constrained | Constrained |  | Private | Private | Greenfield | No | No
201509 | Linlathen House |  | Land To East Of Nursing Home, Linlathen Road | 009059101255 | 346406 | 732975 | 1.5242 | 2015-04-01 | Windfall | Consented (FULL) | <Null> | 10/00298/FULM | 2012-07-24 | Started on site | 2013-08-26 | 60 | 42 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10+Yrs | Market | 42 | 0 | 0 | 0 | Constrained | Constrained |  | Private | Private | Greenfield | No | No

## Removed
Removed - Complete
Site reference | Site Name | LDP2019 reference | Site Address | UPRN | Easting | Northing | Site area (ha) | Year site added | LDP/ Windfall/ Other | Planning Status | Other Detail | Planning application reference | Last planning approval date | Construction Status | Construction Start Date | Site capacity | Units to build | Plots completed in survey year | Total completions | Programmed Y1 | Programmed Y2 | Programmed Y3 | Programmed Y4 | Programmed Y5 | Programmed Y6 | Programmed Y7 | Programmed Y8 | Programmed Y9 | Programmed Y10 | Later Years | Total Programmed | Pipeline Timeframe | Market/ Affordable/ Mixed | Number Market | Number Affordable | No of flats | No of houses | Effective/ Constrained/ Small | Deliverability Status | Action Required | Owner | Developer | Greenfield/ Brownfield | VDL Site | Self Build | Dispute | Demolition Information
201106 | Trades Lane |  | Site of 3 Trades Lane | 009059024533 | 340548 | 730518 | 0.035264 | 2011-04-01 | Windfall | Consented (FULL) | <Null> | 16/01058/FULL | 2017-08-21 | Started on site | 2018-06-24 | 28 | 0 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | Short (1-3yrs) | Affordable | 0 | 28 | 28 | 0 | Effective | Removed |  | Seagate (Dundee) Limited | Hillcrest HA | Brownfield | No | No |  | 13/00786/CON 14/00195/NDOM8
201213 | MOM Phase 4, South East | H22 | Hebrides Drive, South East | 009059105916 | 341518 | 733254 | 0.57888 | 2012-04-01 | LDP | Consented (FULL) | <Null> | 18/00974/FULL, 23/00059/FULL | 2024-01-09 | Started on site | 2024-04-30 | 31 | 0 | 31 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Short (1-3yrs) | Affordable | 0 | 31 | 24 | 7 | Effective | Removed |  | Home Scotland | McTaggart Construction | Brownfield | No | No |  | 16/00589/DOM4
201214 | MOM Phase 4, North East | H21 | Hebrides Drive, North East | 009059105915 | 341531 | 733473 | 0.4467 | 2012-04-01 | LDP | Consented (FULL) | <Null> | 18/00974/FULL, 23/00059/FULL | 2024-01-09 | Started on site | 2024-04-30 | 17 | 0 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Short (1-3yrs) | Affordable | 0 | 17 | 10 | 7 | Effective | Removed |  | Home Scotland | McTaggart Construction | Brownfield | No | No |  | 16/00589/DOM4
201410A | West Grove |  | 10 West Grove Avenue | 009059104789 | 337465 | 730045 | 0.13055 | 2013-12-13 | Windfall | Consented (FULL) | <Null> | 08/00592/FUL, 16/00314/FULL, 19/00376/FULL, 21/00671/FULL | 2022-03-04 | Started on site | 2020-12-18 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Removed |  | Private | Private | Brownfield | No | Single plot
201805G | Gibson Terrace |  | Land to the East of 3 Gibson Terrace | 009059085852 | 341179 | 731912 | 0.13844 | 2017-10-26 | Windfall | Consented (FULL) | <Null> | 17/00594/FULL, 20/00295/FULL | 2020-08-28 | Started on site | 2023-04-10 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Removed |  | Private | Private | Brownfield | No | Single plot
201906 | Langlands Street |  | Workshop and Yard on South Side, Langlands Street | 009059087012 | 341037 | 731374 | 0.14061 | 2018-09-25 | Windfall | Consented (FULL) | <Null> | 18/00500/FULL | 2018-09-25 | Started on site | 2021-07-20 | 16 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | Short (1-3yrs) | Affordable | 0 | 16 | 16 | 0 | Effective | Removed |  | Hillcrest HA | George Martin Builders Ltd | Brownfield | No | No
201908 | Thorter Loan |  | Land to West of Thorter Loan and South of South Victoria Dock Road | 009059101981 | 340968 | 730232 | 0.57494 | 2018-12-20 | Windfall | Consented (FULL) | <Null> | 18/00387/FULM | 2018-12-20 | Started on site | 2019-04-30 | 119 | 0 | 53 | 119 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | Short (1-3yrs) | Affordable | 0 | 53 | 119 | 0 | Effective | Removed |  | Hillcrest HA | Culross Ltd | Brownfield | No | No
201910 | The Old Mill |  | 1 Guthrie Street | 009059021452 | 339735 | 730377 | 0.28532 | 2018-12-14 | Windfall | Consented (FULL) | <Null> | 17/00134/FULL | 2018-12-14 | Started on site | 2021-12-21 | 17 | 0 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Short (1-3yrs) | Market | 17 | 0 | 17 | 0 | Effective | Removed |  | Ramsay Properties Ltd | Ramsay Properties Ltd | Brownfield | No | No
202013 | Buttars Loan |  | Land to the East of Buttars Loan and South of Broomlee Road | 009059106452 | 336795 | 731616 | 0.21362 | 2020-01-23 | Windfall | Consented (FULL) | <Null> | 19/00246/FULL | 2020-01-23 | Started on site | 2021-10-18 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 0 | 0 | 0 | 8 | Effective | Removed |  | Green Pads Limited | Hutchinson Building Services Limited | Brownfield | No | No
202051 | Pitkerro Road |  | Land at 114 - 116 Pitkerro Road | 009059107075 | 342348 | 732644 | 0.73253 | 2020-07-10 | Windfall | Consented (FULL) | <Null> | 20/00052/FULL, 20/00777/FULL | 2021-02-02 | Started on site | 2024-03-11 | 21 | 0 | 21 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | Short (1-3yrs) | Affordable | 0 | 21 | 8 | 13 | Effective | Removed |  | Angus HA | Angus HA | Brownfield | No | No
202106 | Former Park Hotel |  | Park House Hotel, 40 Coupar Angus Road | 009059108014 | 337386 | 732179 | 0.2112 | 2021-08-01 | Windfall | Consented (FULL) | <Null> | 20/00591/FULL | 2021-08-17 | Started on site | 2023-08-14 | 18 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Affordable | 0 | 18 | 18 | 0 | Effective | Removed |  | Redwood Birkhill Ltd | Hillcrest HA | Brownfield | No | No |  | 18/00748/NDOM5
202202 | Former Factory |  | Site Of Former Factory, Ballindean Road | 009059108191 | 343400 | 732158 | 2.1001 | 2022-03-16 | Windfall | Consented (FULL) | <Null> | 21/00602/FULM | 2022-03-16 | Started on site | 2023-01-10 | 67 | 0 | 39 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Affordable | 0 | 67 | 24 | 43 | Effective | Removed |  | Caledonia HA | Culross Ltd | Brownfield | No | No
202311 | Lochee Road |  | 142A Lochee Road | 009059074927 | 338908 | 730689 | 0.020025 | 2023-03-08 | Windfall | Consented (FULL) | <Null> | 22/00485/FULL | 2023-03-08 | Started on site | 2023-05-15 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Removed |  | Private | Private | Brownfield | No | Single plot
202417 | Cleghorn Street |  | 36 - 38 Cleghorn Street | 009059021002 | 338788 | 730722 | 0.0059335 | 2024-08-12 | Windfall | Consented (FULL) |  | 24/00506/FULL | 2024-10-08 | Started on site | 2025-07-09 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Removed |  | Private | Private | Brownfield | No | Single plot
202504 | 40G Baldovan Terrace |  | 40G Baldovan Terrace | 009059083257 | 341268 | 731606 | 0.011418 | 2025-05-23 | Windfall | Consented (FULL) |  | 25/00062/FULL | 2025-05-23 | Started on site |  | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market |  |  | 2 | 0 | Small | Removed |  | Private | Private | Brownfield | No | No
202516 | King Street | . | 17 - 19 King Street | 009059061970 | 340540 | 730690 | 0.049609 | 2021-10-21 |  | Consented (FULL) |  | 21/00225/FULL | 2021-10-21 | Started on site | 2023-05-17 | 10 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Short (1-3yrs) | Market |  |  | 10 | 0 | Effective | Removed |  |  |  | Brownfield | No | No
202517 | Brook Street |  | 217 Brook Street, Broughty Ferry | 009059042381 | 346185 | 730924 | 0.01411 | 2024-08-09 |  | Consented (FULL) |  | 23/00537/FULL | 2024-08-09 | Started on site | 2025-04-23 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Short (1-3yrs) | Market | 2 |  | 2 | 0 | Small | Removed |  |  |  | Brownfield | No | No
[16 empty] | 360 | 0 | 266 | 360
Removed - Expired
Site reference | Site Name | LDP2019 reference | Site Address | UPRN | Easting | Northing | Site area (ha) | Year site added | LDP/ Windfall/ Other | Planning Status | Other Detail | Planning application reference | Last planning approval date | Construction Status | Construction Start Date | Site capacity | Units to build | Plots completed in survey year | Total completions | Programmed Y1 | Programmed Y2 | Programmed Y3 | Programmed Y4 | Programmed Y5 | Programmed Y6 | Programmed Y7 | Programmed Y8 | Programmed Y9 | Programmed Y10 | Later Years | Total Programmed | Pipeline Timeframe | Market/ Affordable/ Mixed | Number Market | Number Affordable | No of flats | No of houses | Effective/ Constrained/ Small | Deliverability Status | Action Required | Owner | Developer | Greenfield/ Brownfield | VDL Site | Self Build | Dispute | Demolition Information
201705B | Brook Street |  | 2/2, 197 Brook Street, Broughty Ferry | 009059077803 | 346151 | 730939 | 0.033857 | 2010-04-08 | Windfall | Consented (FULL) |  | 10/00066/FULL, 13/00139FULL, 16/00488/FULL, 19/00185/FULL, 22/00283/FULL | 2022-06-02 | Not yet started |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Small | Removed |  | Private | Private | Brownfield | No | Single plot
202053 | Murrayfield Place |  | Land at Murrayfield Place, Murrayfield Drive, Whitfield Avenue and Murrayfield Terrace | 009059106824 | 343109 | 732956 | 2.1982 | 2021-02-18 | Windfall | Consented (FULL) | <Null> | 20/00064/FULL, 22/00239/FULL | 2022-07-25 | Not yet started |  | 42 | 42 | 0 | 0 | 0 | 22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | Short (1-3yrs) | Affordable | 0 | 42 | 32 | 10 | Effective | Removed | Drainage | Dundee City Council | Dundee City Council | Brownfield | Yes | No
202303 | Guthrie Street |  | Premises, 9 Guthrie Street | 009059089090 | 339644 | 730319 | 0.15991 | 2022-09-27 | Windfall | Consented (FULL) | <Null> | 21/00296/FULL | 2022-09-27 | Not yet started |  | 18 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Market | 18 | 0 | 18 | 0 | Effective | Removed |  | Private | Private | Brownfield | No | No
202305 | Balgillo Road |  | Land to South of 157 Balgillo Road, Broughty Ferry | 009059105089 | 346450 | 732090 | 0.10384 | 2022-11-23 | Windfall | Consented (FULL) | <Null> | 22/00503/FULL | 2022-11-23 | Not yet started |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Removed |  | Private | Private | Brownfield | No | Single plot
202309 | Mosque |  | Mosque, 114 Hilltown | 009059086323 | 340168 | 730930 | 0.02379 | 2022-12-22 | Windfall | Consented (FULL) | <Null> | 22/00699/FULL | 2022-12-22 | Not yet started |  | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Short (1-3yrs) | Market | 5 | 0 | 5 | 0 | Effective | Removed |  | Private | Private | Brownfield | No | No
202310 | Candle Lane |  | Car Park, 3 - 7 Candle Lane | 009059090587 | 340567 | 730410 | 0.045363 | 2023-02-10 | Windfall | Consented (FULL) | <Null> | 20/00739/FULL | 2023-02-10 | Not yet started |  | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 8 | 0 | Effective | Removed |  | Murrayfield Properties Ltd | Murrayfield Properties Ltd | Brownfield | No | No
202313 | Mains of Gray Farm |  | Land to the South of Mains Of Gray Farm and West of Dykes Of Gray Road | 009059082773 | 333577 | 732048 | 0.28448 | 2023-03-31 | Windfall | Consented (FULL) | <Null> | 22/00818/FULL | 2023-03-31 | Not yet started |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Small | Removed |  | Private | Private | Greenfield | No | Single plot