## Greenfield
Deliverable and Deliverable with Constraints Greenfield
HLA site reference | Site name | LDP reference | Site address | Easting | Northing | Site area (ha) | Year added to HLA | LDP/ Windfall/ Other | Planning status No consent Pending decision Consented (PPiP) Consented (Full) | Other detail Pre-application refused under appeal | Planning application(s) | Last approval date | Construction status Not yet started Started on site | Year construction started | Site capacity | Remaining capacity | Completions in audit year | Total completions | Programming Y1 (25-26) | Programming Y2 (26-27) | Programming Y3 (27-28) | Programming Y4 (28-29) | Programming Y5 (29-30) | Programming Y6 (30-31) | Programming Y7 (31-32) | Programming Y8 (32-33) | Programming Y9 (33-34) | Programming Y10 (34-35) | Later years | Total programming | Pipeline timeframe Short (1-3 Yrs) Medium (4-6 Yrs) Long (7-10 Yrs) | Market/ Affordable/ Mixed | Number market | Number affordable | Number of flats | Number of houses | Deliverability status Deliverable, Deliverable with constraints, Constrained, Undeliverable, Removed | Action required Action Required To Support Delivery | Owner | Developer | Greenfield/ Brownfield | VDL | Self build | Dispute If the information provided within the HLA remains disputed and by who | Demolition Have list references where there was an application
200356A | Western Gateway, South Gray Village |  | South Gray Village, Dykes of Gray Road | 334131 | 731821 | 19.3417 | 2016-03-11 | Windfall | Consented (FULL) |  | 15/00121/FULM, 16/00370/FULL, 16/01012/MDPO, 17/00938/FULL, 18/00539/FULL, 24/00420/FULL | 2024-09-16 | Started on site | 2017-03-01 | 341 | 76 | 0 | 265 | 24 | 24 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | Short (1-3yrs) | Market | 76 | 0 | 58 | 146 | Deliverable |  | Springfield | Springfield | Greenfield | No | No
200408 | Western Gateway, West of Dykes of Gray Road |  | Swallow, Land to West of Dykes of Gray Road, Western Gateway | 334038 | 731320 | 24.3312 | 2015-06-03 | Windfall | Consented (FULL) |  | 14/00205/FULM, 16/01023/FULL, 17/00409/MDPO, 23/00168/FULL | 2017-07-19 | Started on site | 2015-07-20 | 230 | 78 | 11 | 152 | 26 | 0 | 0 | 0 | 24 | 28 | 0 | 0 | 0 | 0 | 0 | 78 | Medium (4-6Yrs) | Market | 78 | 0 | 0 | 85 | Deliverable |  | Springfield | Springfield | Greenfield | No | No
200738 | Western Gateway, Liff |  | Liff Phase 2, Dykes of Gray Road | 334379 | 732314 | 7.8207 | 2016-06-17 | Windfall | Consented (FULL) |  | 15/00410/FULM, 18/00992/FULL | 2019-02-06 | Started on site | 2019-07-30 | 100 | 100 | 0 | 0 | 0 | 12 | 29 | 34 | 21 | 4 | 0 | 0 | 0 | 0 | 0 | 100 | Medium (4-6Yrs) | Market | 100 | 0 | 0 | 100 | Deliverable |  | Barratt & David Wilson Homes North Scotland | Barratt & David Wilson Homes North Scotland | Greenfield | No | No
201423 | Pitkerro Mill |  | Land to the West of Pitkerro Mill, Kellas Road | 345078 | 733464 | 1.0007 | 2016-07-20 | Windfall | Consented (FULL) |  | 16/00394/FULL | 2016-07-20 | Started on site | 2023-08-14 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Short (1-3yrs) | Market | 6 | 0 | 0 | 6 | Deliverable |  | South Tay (Dundee) Ltd | South Tay (Dundee) Ltd | Greenfield | No | No
201821 | Western Gateway, East of Dykes Of Gray Road | H42 | Land to South of West Green Park and East of Dykes Of Gray Road | 334219 | 732498 | 3.2797 | 2018-04-01 | LDP | Consented (PPiP) |  | 23/00617/PPPM |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Medium (4-6Yrs) | Market | 30 | 0 | 0 | 30 | Deliverable |  | NHS Tayside | NHS Tayside | Greenfield | No | No
201822 | Western Gateway, Dykes of Gray, North East | H43 | Dykes of Gray, North East | 334471 | 732016 | 13.4423 | 2018-12-17 | LDP | Consented (FULL) |  | 18/01056/FULM, 25/00184/PAN | 2025-02-25 | Not yet started |  | 215 | 215 | 0 | 0 | 0 | 0 | 13 | 34 | 40 | 40 | 40 | 40 | 8 | 0 | 0 | 215 | Long (7-10Yrs) | Market | 215 | 0 | 50 | 165 | Deliverable |  | Barratt & David Wilson Homes North Scotland | Barratt & David Wilson Homes North Scotland | Greenfield | No | No
201823 | Baldragon Farm | H44 | Land to West of St Martin Crescent and North of Adam Crescent | 337401 | 734790 | 6.2216 | 2018-04-01 | LDP | Consented (FULL) |  | 19/00707/FULM, 20/00771/FULL | 2020-08-20 | Started on site | 2021-03-04 | 120 | 67 | 23 | 53 | 23 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | Short (1-3yrs) | Market | 67 | 0 | 0 | 120 | Deliverable |  | Avant Homes Scotland | Avant Homes Scotland | Greenfield | No | No
201824B | Ballumbie Road Phase 2 | H45 | Land to East of Ballumbie Road | 344607 | 733962 | 7.4872 | 2021-05-21 | LDP | Consented (FULL) |  | 20/00423/FULM, 24/00726/FULL | 2021-05-21 | Not yet started |  | 150 | 150 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 6 | 0 | 0 | 0 | 0 | 150 | Long (7-10Yrs) | Market | 150 | 0 | 0 | 150 | Deliverable |  | Persimmon Homes North Scotland | Persimmon Homes North Scotland | Greenfield | No | No
201829 | Western Gateway, Dykes of Gray, North West | H41 | Dykes of Gray, North West | 333717 | 731646 | 21.9833 | 2018-01-11 | LDP | No consent |  |  |  | Not yet started |  | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 0 | 0 | 0 | 0 | 216 | 250 | 10+Yrs | Market | 250 | 0 | 0 | 250 | Deliverable |  | Springfield | Springfield | Greenfield | No | No
201830 | Linlathen | H46 | Linlathen Road, Broughty Ferry | 346394 | 733242 | 15.8973 | 2018-06-25 | LDP | Consented (FULL) |  | 18/00115/FULM, 19/00799/FULM, 21/00322/FULL, 21/00376/FULL, 21/00677/FULL, 21/00713/FULL | 2021-07-01 | Started on site | 2021-01-04 | 250 | 1 | 15 | 249 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Short (1-3yrs) | Market | 1 | 0 | 0 | 250 | Deliverable |  | Kirkwood Homes | Kirkwood Homes | Greenfield | No | No

## Brownfield
Deliverable and Deliverable with Constraints Brownfield
HLA site reference | Site name | LDP reference | Site address | Easting | Northing | Site area (ha) | Year added to HLA | LDP/ Windfall/ Other | Planning status No consent Pending decision Consented (PPiP) Consented (Full) | Other detail Pre-application refused under appeal | Planning application(s) | Last approval date | Construction status Not yet started Started on site | Year construction started | Site capacity | Remaining capacity | Completions in audit year | Total completions | Programming Y1 (25-26) | Programming Y2 (26-27) | Programming Y3 (27-28) | Programming Y4 (28-29) | Programming Y5 (29-30) | Programming Y6 (30-31) | Programming Y7 (31-32) | Programming Y8 (32-33) | Programming Y9 (33-34) | Programming Y10 (34-35) | Later years | Total programming Not required our use only | Pipeline timeframe Short (1-3 Yrs) Medium (4-6 Yrs) Long (7-10 Yrs) | Market/ Affordable/ Mixed | Number market | Number affordable | Number of flats | Number of houses | Deliverability status Deliverable, Deliverable with constraints, Constrained, Undeliverable, Removed | Action required Action Required To Support Delivery | Owner | Developer | Greenfield/ Brownfield | VDL | Self build | Dispute If the information provided within the HLA remains disputed and by who | Demolition Have list references where there was an application
201510 | Lochee District Centre | H06 | Lochee District Centre, Lochee High Street | 337857 | 731572 | 6.1424 | 2015-04-01 | LDP | Consented (FULL) |  | 13/00678/FULL, 15/00079/FULL, 19/00738/FULL | 2020-01-27 | Not yet started |  | 40 | 40 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | Medium (4-6Yrs) | Affordable | 0 | 40 |  |  | Deliverable with constraints | Drainage solution being investigated | Dundee City Council | Hillcrest HA | Brownfield | Yes | No
201827 | Kellyfield | H33 | Drumgeith Road | 344237 | 733239 | 8.4241 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 100 | Medium (4-6Yrs) | Market | 100 | 0 |  |  | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
202108 | Former Tay Rope Works |  | Land at Former Tay Rope Works, Magdalen Yard Road | 339151 | 729525 | 0.25114 | 2021-04-21 | Windfall | Consented (FULL) |  | 19/00297/FULL | 2021-04-21 | Started on site | 2023-03-27 | 9 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | Short (1-3yrs) | Market | 9 | 0 | 4 | 5 | Deliverable |  | F & H Property | F & H Property | Brownfield | No | No
202414 | Ferry House Residential Home |  | Ferry House Residential Home, 8 Gray Street, Broughty Ferry | 346265 | 730684 | 0.062191 | 2024-07-05 | Windfall | Consented (FULL) |  | 24/00453/FULL | 2025-02-28 | Not yet started |  | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | Short (1-3yrs) | Affordable | 0 | 7 | 7 | 0 | Deliverable |  | Hillcrest HA | Hillcrest HA | Brownfield | No | No
200347 | Armistead |  | 94 Monifieth Road | 347412 | 731144 | 1.0067 | 2013-12-17 | Windfall | Consented (FULL) |  | 13/00642/FULL, 16/00179/FULL, 21/00904/FULL | 2022-04-15 | Started on site | 2017-06-14 | 26 | 19 | 7 | 7 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | Short (1-3yrs) | Market | 19 | 0 | 23 | 3 | Deliverable |  | H & H Properties Ltd | H & H Properties Ltd | Brownfield | No | No |  | 13/00642/FULL, 15/00790/DOM1
200611 | Former Homebase Site |  | Riverside Drive | 339577 | 729422 | 1.6776 | 2007-06-05 | Windfall | Consented (FULL) |  | 05/00770/FUL, 22/00463/FULL | 2007-06-05 | Started on site | 2012-04-30 | 143 | 56 | 2 | 87 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | Short (1-3yrs) | Market | 56 | 0 | 135 | 8 | Deliverable |  | H & H Properties | H & H Properties | Brownfield | No | No |  | 06/01434/DEMOL
200909 | Former Downfield Primary School | H11 | East School Road | 338919 | 733132 | 1.2778 | 2009-04-01 | LDP | Consented (FULL) |  | 20/00076/FULL | 2020-11-18 | Started on site | 2023-08-23 | 23 | 23 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | Short (1-3yrs) | Market | 23 | 0 | 0 | 23 | Deliverable |  | H & H Properties | H & H Properties | Brownfield | No | No |  | 08/00848/DEMOL
200913 | Former Lawside Academy | H09 | Rannoch Road | 338363 | 733094 | 4.0249 | 2009-04-01 | LDP | No consent |  |  |  | Not yet started |  | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 70 | Medium (4-6Yrs) | Market | 70 | 0 |  |  | Deliverable with constraints |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201008 | Bowling Green East | H31 | Lothian Crescent | 343913 | 733373 | 1.3369 | 2010-04-01 | LDP | No consent |  |  |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Short (1-3yrs) | Market | 30 | 0 |  |  | Deliverable with constraints |  | Dundee City Council | Dundee City Council | Brownfield | No | No
201010 | Tranent Grove, Phase 3 | H28 | Tranent Grove | 343320 | 733503 | 3.7588 | 2010-04-01 | LDP | Consented (FULL) |  | 22/00461/FULL, 24/00424/FULL | 2022-12-16 | Not yet started |  | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 31 | 0 | 0 | 0 | 0 | 53 | Long (7-10Yrs) | Market | 53 | 0 |  |  | Deliverable |  | Dundee City Council | Discovery Homes Ltd | Brownfield | Yes | No
201010A | Tranent Grove, Phase 1 | H28 | Land North Of Lothian Crescent and South Of Tranent Grove | 343303 | 733461 | 1.3436 | 2022-12-16 | LDP | Consented (FULL) |  | 22/00461/FULL | 2022-12-16 | Not yet started |  | 17 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Short (1-3yrs) | Market | 17 | 0 | 0 | 17 | Deliverable |  | Discovery Homes Ltd | Discovery Homes Ltd | Brownfield | Yes | No
201010B | Tranent Grove, Phase 2 | H28 | Land At Salton Crescent and Tranent Grove and North Of Lothian Crescent | 343248 | 733578 | 0 | 2025-01-16 | LDP | Consented (FULL) |  | 24/00424/FULL | 2025-01-16 | Not yet started |  | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Medium (4-6Yrs) | Market | 17 | 0 | 0 | 17 | Deliverable |  | Discovery Homes Ltd | Discovery Homes Ltd | Brownfield | Yes | No
201011A | Whitfield Primary School South | H27 | Site Of Whitfield Primary School, Whitfield Drive (South) | 343204 | 733328 | 1.2007 | 2023-09-13 | LDP | Consented (FULL) |  | 19/00716/FULL | 2023-09-13 | Started on site | 2024-08-19 | 18 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Affordable | 0 | 18 | 8 | 10 | Deliverable |  | Angus HA | Angus HA | Brownfield | Yes | No |  | 12/00550/DEMOL
201011B | Whitfield Primary School North | H27 | Site Of Whitfield Primary School, Whitfield Drive (North) | 343234 | 733380 | 1.1547 | 2023-09-13 | LDP | Consented (FULL) |  | 19/00776/FULL | 2023-09-13 | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Medium (4-6Yrs) | Market | 30 | 0 | 0 | 30 | Deliverable |  | George Martin Builders Ltd | George Martin Builders Ltd | Brownfield | Yes | No
201012 | Former Whitfield Shopping Centre | H25 | Whitfield Drive and Lothian Crescent | 343056 | 733375 | 1.8274 | 2010-04-01 | LDP | No consent | Pre-application | PREAPP/041/2021, 19/00716/FULL (Part) |  | Started on site | 2024-08-19 | 30 | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Short (1-3yrs) | Mixed | 18 | 12 | 12 | 18 | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201102 | Dura Street |  | 3 Dura Street | 340858 | 731298 | 0.07577 | 2010-12-21 | Windfall | Consented (FULL) |  | 10/00676/FULL, 13/00824/FULL, 17/00014/FULL, 20/00018/FULL, 23/00153/FULL | 2023-06-29 | Not yet started |  | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 8 | 0 | Deliverable |  | B & L Whittet Ltd | B & L Whittet Ltd | Brownfield | No | No |  | existing car sales & MOT garage
201106 | Trades Lane |  | Site of 3 Trades Lane | 340548 | 730518 | 0.035264 | 2011-04-01 | Windfall | Consented (FULL) |  | 16/01058/FULL | 2017-08-21 | Started on site | 2018-06-24 | 28 | 28 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | Short (1-3yrs) | Affordable | 0 | 28 | 28 | 0 | Deliverable |  | Seagate (Dundee) Limited | Hillcrest HA | Brownfield | No | No |  | 13/00786/CON, 14/00195/NDOM8
201109 | Central Waterfront Site 6, Thomson Avenue | H17 | Central Waterfront, Thomson Avenue | 340509 | 729995 | 23.9694 | 2011-04-01 | LDP | Consented (FULL) |  | 17/00113/FULM, 18/00400/FULL | 2020-10-16 | Started on site | 2022-10-17 | 276 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 70 | 70 | 76 | 0 | 0 | 0 | 276 | Long (7-10Yrs) | Mixed |  |  | 276 | 0 | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201109A | Central Waterfront Site 6, Riverside Esplanade | H17 | Waterfront Site 6, Riverside Esplanade | 340454 | 729970 | 0.7231 | 2017-06-23 | LDP | Consented (FULL) |  | 17/00113/FULM, 18/00400/FULL | 2017-06-23 | Not yet started |  | 99 | 99 | 0 | 0 | 0 | 0 | 50 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | Medium (4-6Yrs) | Market | 99 | 0 | 99 | 0 | Deliverable |  | Dundee City Council | Robertson Living | Brownfield | No | No
201109B | Central Waterfront Site 6, Dock Street | H17 | Harbour Chambers/Customs House, Dock Street | 340688 | 730304 | 0.37882 | 2020-10-16 | LDP | Consented (FULL) |  | 20/00399/FULL | 2020-10-16 | Started on site | 2022-10-17 | 49 | 49 | 0 | 0 | 0 | 0 | 20 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | Medium (4-6Yrs) | Market | 49 | 0 | 49 | 0 | Deliverable |  | Alicydon Ltd | Alicydon Ltd | Brownfield | No | No
201110 | Former Mossgiel Primary School | H23 | Ballochmyle Drive | 341769 | 732646 | 1.4577 | 2011-04-01 | LDP | Pending decision | Pre-application | PREAPP/043/2021, 22/00637/FULL |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Medium (4-6Yrs) | Affordable | 0 | 30 | 0 | 30 | Deliverable with constraints | Drainage solution being investigated | Dundee City Council | Abertay HA | Brownfield | Yes | No
201213 | MOM Phase 4, South East | H22 | Hebrides Drive, South East | 341518 | 733254 | 0.57888 | 2012-04-01 | LDP | Consented (FULL) |  | 18/00974/FULL, 23/00059/FULL | 2024-01-09 | Started on site | 2024-04-30 | 31 | 31 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | Short (1-3yrs) | Affordable | 0 | 31 | 24 | 7 | Deliverable |  | Home Scotland | McTaggart Construction | Brownfield | No | No |  | 16/00589/DOM4
201214 | MOM Phase 4, North East | H21 | Hebrides Drive, North East | 341531 | 733473 | 0.4467 | 2012-04-01 | LDP | Consented (FULL) |  | 18/00974/FULL, 23/00059/FULL | 2024-01-09 | Started on site | 2024-04-30 | 17 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Short (1-3yrs) | Affordable | 0 | 17 | 10 | 7 | Deliverable |  | Home Scotland | McTaggart Construction | Brownfield | No | No |  | 16/00589/DOM4
201221 | MOM Phase 4, West | H20 | Hebrides Drive, West | 341048 | 733472 | 0.63833 | 2012-04-01 | LDP | No consent | Pre-application | PREAPP/078/2022 |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10+Yrs | Market | 10 | 0 |  |  | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201417 | Former Lochee Primary School | H05 | Donals Street and South Road | 337330 | 731477 | 1.7818 | 2014-04-01 | LDP | Consented (FULL) |  | 22/00402/FULL | 2023-11-01 | Not yet started |  | 39 | 39 | 0 | 0 | 0 | 20 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | Short (1-3yrs) | Market | 39 | 0 | 0 | 39 | Deliverable |  | H & H Properties | H & H Properties | Brownfield | Yes | No
201813 | Former Maxwelltown Multis | H16 | Alexander Street | 340172 | 731036 | 0.61367 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 30 | Long (7-10Yrs) | Market | 30 | 0 |  |  | Deliverable | Drainage solution being investigated | Dundee City Council | Dundee City Council | Brownfield | Yes | No
201814 | Former Gowriehill Primary School | H34 | Etive Gardens | 335665 | 731239 | 1.6697 | 2018-04-01 | LDP | Pending decision |  | PREAPP/029/2022, 24/00140/PAN, 24/00366/FULL | 2024-07-16 | Not yet started |  | 35 | 35 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | Short (1-3yrs) | Affordable | 0 | 35 |  |  | Deliverable |  | Dundee City Council | Angus HA | Brownfield | Yes | No |  | 18/00051/NDOM6
201815 | Former Hillside Primary School | H35 | Denoon Terrace | 336897 | 731187 | 1.9738 | 2018-04-01 | LDP | Pending decision | Pre-application | PREAPP/016/2024, 25/00134/FULL |  | Not yet started |  | 45 | 45 | 0 | 0 | 0 | 0 | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | Medium (4-6Yrs) | Market | 45 | 0 |  |  | Deliverable |  | Dundee City Council | H & H Properties | Brownfield | Yes | No
201816 | Former St Mary's Infant School | H36 | Former St Mary's Infant School, High Street, Lochee | 337998 | 731337 | 0.36187 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Short (1-3yrs) | Affordable | 0 | 10 |  |  | Deliverable with constraints | Drainage solution being investigated | Dundee City Council | Hillcrest HA | Brownfield | Yes | No
201817 | Former Baldragon Academy | H37 | Burn Street | 339111 | 733973 | 4.926 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 70 | 70 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | Medium (4-6Yrs) | Market | 70 | 0 |  |  | Deliverable | Marketing of site for housing | Dundee City Council | Dundee City Council | Brownfield | No | No
201825 | Former Railyards | H14 | Greenmarket | 339467 | 729510 | 2.1768 | 2018-04-01 | LDP | No consent |  |  |  | Not yet started |  | 110 | 110 | 0 | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | Medium (4-6Yrs) | Market | 110 | 0 |  |  | Deliverable with constraints |  | Scottish Enterprise |  | Brownfield | Yes | No
201826C | Summerfield Gardens | H29 | Land to West Of Summerfield Avenue at Summerfield Gardens | 343614 | 733089 | 1.9422 | 2022-06-13 | LDP | Consented (FULL) |  | 21/00736/FULL | 2022-06-13 | Started on site | 2024-03-12 | 34 | 28 | 6 | 6 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | Short (1-3yrs) | Market | 28 | 0 | 0 | 34 | Deliverable |  | Invertay Homes Ltd | Invertay Homes Ltd | Brownfield | Yes | No
201906 | Langlands Street |  | Workshop and Yard on South Side, Langlands Street | 341037 | 731374 | 0.14061 | 2018-09-25 | Windfall | Consented (FULL) |  | 18/00500/FULL | 2018-09-25 | Started on site | 2021-07-20 | 16 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | Short (1-3yrs) | Affordable | 0 | 16 | 16 | 0 | Deliverable |  | Hillcrest HA | George Martin Builders Ltd | Brownfield | No | No
201908 | Thorter Loan |  | Land to West of Thorter Loan and South of South Victoria Dock Road | 340968 | 730232 | 0.57494 | 2018-12-20 | Windfall | Consented (FULL) |  | 18/00387/FULM | 2018-12-20 | Started on site | 2019-04-30 | 119 | 53 | 0 | 66 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | Short (1-3yrs) | Affordable | 0 | 53 | 119 | 0 | Deliverable |  | Hillcrest HA | Culross Ltd | Brownfield | No | No
201910 | The Old Mill |  | 1 Guthrie Street | 339735 | 730377 | 0.28532 | 2018-12-14 | Windfall | Consented (FULL) |  | 17/00134/FULL | 2018-12-14 | Started on site | 2021-12-21 | 17 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Short (1-3yrs) | Market | 17 | 0 | 17 | 0 | Deliverable |  | Ramsay Properties Ltd | Ramsay Properties Ltd | Brownfield | No | No
201912 | Ellengowan Drive |  | South Of Arbroath Road, West Of Dalkeith Road, Ellengowan Rd | 341769 | 731105 | 3.9484 | 2019-04-09 | Windfall | Consented (FULL) |  | 18/00487/FULM | 2019-04-09 | Started on site | 2020-08-28 | 130 | 60 | 0 | 70 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | Short (1-3yrs) | Affordable | 0 | 60 | 48 | 22 | Deliverable |  | Hillcrest HA | Hillcrest HA | Brownfield | No | No |  | 18/00752/DOM1, 18/00753/DOM1, 24/00123/DOM4
202009 | Taybank Works |  | Unit 23, Taybank Works, Morgan Street | 341351 | 731255 | 0.91844 | 2019-09-18 | Windfall | Consented (FULL) |  | 19/00227/FULL, 20/00039/FULL, 20/00306/FULL, 21/00326/FULL | 2021-11-19 | Not yet started |  | 37 | 37 | 0 | 0 | 0 | 17 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | Short (1-3yrs) | Affordable | 0 | 37 | 16 | 21 | Deliverable |  | Caledonia Housing Association | Caledonia Housing Association | Brownfield | No | No |  | 19/00364/NDOM8
202012 | Former Stewart House |  | Land at Former Stewart House, Kingsway East | 342852 | 731829 | 2.8817 | 2019-12-18 | Windfall | Consented (FULL) |  | 19/00687/FULM, 23/00449/FULL | 2023-09-07 | Started on site | 2023-07-24 | 71 | 49 | 22 | 22 | 35 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | Short (1-3yrs) | Market | 49 | 0 | 0 | 71 | Deliverable |  | Persimmon Homes North Scotland | Persimmon Homes North Scotland | Brownfield | No | No |  | 17/00183/NDOM7
202013 | Buttars Loan |  | Land to the East of Buttars Loan and South of Broomlee Road | 336795 | 731616 | 0.21362 | 2020-01-23 | Windfall | Consented (FULL) |  | 19/00246/FULL | 2020-01-23 | Started on site | 2021-10-18 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 0 | 8 | Deliverable |  | Green Pads Limited | Hutchinson Building Services Limited | Brownfield | No | No
202024 | Land to North of Pitkerro Road |  | Land to North of Pitkerro Road and East of Longhaugh Road | 342795 | 732954 | 1.02 | 2020-05-21 | Windfall | Consented (FULL) |  | 19/00063/FULL | 2020-05-21 | Started on site | 2021-08-02 | 14 | 2 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Short (1-3yrs) | Market | 2 | 0 | 0 | 14 | Deliverable |  | Longhaugh Developments Ltd | Longhaugh Developments Ltd | Brownfield | No | No
202030 | Gellatly Street |  | 3 Gellatly Street | 340610 | 730351 | 0.12902 | 2020-07-30 | Windfall | Consented (FULL) |  | 19/00502/FULL, 21/00215/FULL | 2021-12-07 | Started on site | 2023-03-01 | 49 | 49 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | Short (1-3yrs) | Market | 49 | 0 | 49 | 0 | Deliverable |  | McGill (Dock Street) Ltd | McGill (Dock Street) Ltd | Brownfield | No | No
202051 | Pitkerro Road |  | Land at 114 - 116 Pitkerro Road | 342348 | 732644 | 0.73952 | 2020-07-10 | Windfall | Consented (FULL) |  | 20/00052/FULL, 20/00777/FULL | 2021-02-02 | Started on site | 2024-03-11 | 21 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | Short (1-3yrs) | Affordable | 0 | 21 | 8 | 13 | Deliverable |  | Angus HA | Angus HA | Brownfield | No | No
202053 | Whitfield Avenue |  | Land at Murrayfield Place, Murrayfield Drive, Whitfield Avenue and Murrayfield Terrace | 343109 | 732956 | 2.1982 | 2021-02-18 | Windfall | Consented (FULL) |  | 20/00064/FULL, 22/00239/FULL | 2022-07-25 | Not yet started |  | 42 | 42 | 0 | 0 | 22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | Short (1-3yrs) | Affordable | 0 | 42 | 32 | 10 | Deliverable |  | Dundee City Council | Dundee City Council | Brownfield | Yes | No
202061B | Dalkeith Road |  | 69 Dalkeith Road | 341712 | 731577 | 0.22415 | 2020-10-22 | Windfall | Consented (FULL) |  | 20/00142/FULL | 2020-10-22 | Started on site | 2021-09-29 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 4 | 0 | 3 | 1 | Deliverable |  | Marvend Ltd | Marvend Ltd | Brownfield | No | No
202065 | Former Tennis Club |  | 57 Dalkeith Road | 341769 | 731399 | 0.26635 | 2020-11-18 | Windfall | Consented (FULL) |  | 20/00209/FULL | 2020-11-18 | Started on site | 2024-05-01 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 0 | 8 | Deliverable |  | Private | Private | Brownfield | No | No
202104 | Former Rosebank Primary School |  | Land at Rosebank Road | 339990 | 730905 | 1.3421 | 2021-06-16 | Windfall | Consented (FULL) |  | 21/00011/FULL | 2021-06-16 | Started on site | 2022-06-10 | 40 | 27 | 5 | 13 | 16 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | Short (1-3yrs) | Market | 27 | 0 | 0 | 40 | Deliverable |  | Discovery Homes (Dundee) Ltd | Discovery Homes (Dundee) Ltd | Brownfield | No | No
202106 | Former Park Hotel |  | Park House Hotel, 40 Coupar Angus Road | 337386 | 732179 | 0.2112 | 2021-08-01 | Windfall | Consented (FULL) |  | 20/00591/FULL | 2021-08-17 | Started on site | 2023-08-14 | 18 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Affordable | 0 | 18 | 18 | 0 | Deliverable |  | Redwood Birkhill Ltd | Redwood Birkhill Ltd | Brownfield | No | No |  | 18/00748/NDOM5
202115 | Whitehall Crescent |  | 3 Whitehall Crescent | 340357 | 730131 | 0.028412 | 2021-11-18 | Windfall | Consented (FULL) |  | 21/00636/FULL | 2021-11-18 | Started on site | 2024-06-01 | 14 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | Short (1-3yrs) | Market | 14 | 0 | 14 | 0 | Deliverable |  | Joup Property Ltd | Joup Property Ltd | Brownfield | No | No
202202 | Ballindean Road |  | Site Of Former Factory, Ballindean Road | 343400 | 732158 | 2.1001 | 2022-03-16 | Windfall | Consented (FULL) |  | 21/00602/FULM | 2022-03-16 | Started on site | 2023-01-10 | 67 | 67 | 28 | 0 | 55 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | Short (1-3yrs) | Affordable | 0 | 67 | 24 | 43 | Deliverable |  | Caledonia HA | Culross Ltd | Brownfield | No | No
202204 | Site of James Keiller Buildings |  | 32 - 34 Mains Loan | 340952 | 732266 | 6.3067 | 2022-02-17 | Windfall | Consented (FULL) |  | 20/00098/FULM, 22/00627/FULL | 2024-01-19 | Started on site | 2022-11-15 | 223 | 133 | 62 | 90 | 52 | 65 | 41 | 30 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | Medium (4-6Yrs) | Market | 133 | 0 | 56 | 167 | Deliverable |  | Marketgait Developments | Barratt & David Wilson Homes North Scotland | Brownfield | No | No |  | 07/00233/DEMOL
202205 | Burnside Street |  | 55 Burnside Street | 338192 | 731432 | 0.57137 | 2022-03-17 | Windfall | Consented (FULL) |  | 21/00857/FULM | 2022-03-17 | Started on site | 2024-08-19 | 54 | 54 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | Short (1-3yrs) | Affordable | 0 | 54 | 54 | 0 | Deliverable |  | Hillcrest HA | George Martin Builders | Brownfield | Yes | No
202303 | Guthrie Street |  | Premises, 9 Guthrie Street | 339644 | 730319 | 0.15991 | 2022-09-27 | Windfall | Consented (FULL) |  | 21/00296/FULL | 2022-09-27 | Not yet started |  | 18 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Market | 18 | 0 | 18 | 0 | Deliverable |  | Private | Private | Brownfield | No | No
202308 | Mains of Balgay |  | Vacant Workshop and Store, Mains Of Balgay, Elliot Road | 337381 | 730420 | 0.30628 | 2022-12-22 | Windfall | Consented (FULL) |  | 22/00563/FULL | 2022-12-22 | Not yet started |  | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Short (1-3yrs) | Market | 5 | 0 | 0 | 5 | Deliverable |  | Private | Private | Brownfield | No | No |  | Proposed demolition of former workshop and stores
202309 | Mosque |  | Mosque, 114 Hilltown | 340168 | 730930 | 0.02379 | 2022-12-22 | Windfall | Consented (FULL) |  | 22/00699/FULL | 2022-12-22 | Not yet started |  | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Short (1-3yrs) | Market | 5 | 0 | 5 | 0 | Deliverable |  | Private | Private | Brownfield | No | No
202310 | Candle Lane |  | Car Park, 3 - 7 Candle Lane | 340567 | 730410 | 0.045363 | 2023-02-10 | Windfall | Consented (FULL) |  | 20/00739/FULL | 2023-02-10 | Not yet started |  | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 8 | 0 | Deliverable |  | Murrayfield Properties Ltd | Murrayfield Properties Ltd | Brownfield | No | No
202319 | Donalds Lane |  | Site Of Former 6 Donalds Lane | 336880 | 731887 | 0.21219 | 2023-08-10 | Windfall | Consented (FULL) |  | 22/00376/FULL | 2023-08-10 | Not yet started |  | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 4 | 0 | 0 | 4 | Deliverable |  | H & H Properties UK Ltd | H & H Properties UK Ltd | Brownfield | Yes | No
202322 | The High Kirk |  | The High Kirk, 119A Kinghorne Road | 339491 | 731290 | 0.2027 | 2023-10-12 | Windfall | Consented (FULL) |  | 23/00389/FULL | 2023-10-12 | Started on site | 2024-08-14 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Market | 8 | 0 | 8 | 0 | Deliverable |  | David Gray Construction Ltd | David Gray Construction Ltd | Brownfield | No | No |  | Demolition of ancillary hall building
202324 | The Rock |  | Land At Dickson Avenue | 336124 | 731003 | 0.15234 | 2023-11-07 | Windfall | Consented (FULL) |  | 23/00510/FULL | 2023-11-07 | Not yet started |  | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | Short (1-3yrs) | Market | 16 | 0 | 16 | 0 | Deliverable |  | Rock Developments (Scotland) Ltd | Rock Developments (Scotland) Ltd | Brownfield | No | No
202401 | Caird Rest |  | Caird Rest, 172 Nethergate | 339852 | 729813 | 0.2397 | 2024-01-10 | Windfall | Consented (FULL) |  | 23/00451/FULL | 2024-01-10 | Not yet started |  | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Short (1-3yrs) | Market | 5 | 0 | 5 | 0 | Deliverable |  | Private | Private | Brownfield | No | No
202408 | East Port House |  | East Port House, 65 - 67 King Street | 340679 | 730777 | 0.069167 | 2024-04-08 | Windfall | Consented (FULL) |  | 24/00196/FULL | 2024-09-20 | Not yet started |  | 18 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Short (1-3yrs) | Market | 18 | 0 | 18 | 0 | Deliverable |  | Marketgait Developments Ltd | Marketgait Developments Ltd | Brownfield | No | No
202411 | Former Hilltown Market |  | Site Of Former Hilltown Market, Main Street | 340125 | 731525 | 1.6349 | 2024-05-30 | Windfall | Consented (FULL) |  | 23/00208/FULM | 2024-05-30 | Not yet started |  | 131 | 131 | 0 | 0 | 0 | 31 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | Medium (4-6Yrs) | Affordable | 0 | 131 | 122 | 9 | Deliverable |  | Springfield Partnerships | Springfield Partnerships/ Hillcrest HA | Brownfield | Yes | No
202419 | Sangobeg House |  | Sangobeg House, 4 Francis Street | 339571 | 731966 | 0.14222 | 2024-08-20 | Windfall | Consented (FULL) |  | 24/00530/FULL | 2025-01-17 | Not yet started |  | 9 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | Short (1-3yrs) | Market | 9 | 0 | 0 | 0 | Deliverable |  | Sangobeg Developments Ltd | Sangobeg Developments Ltd | Brownfield | No | No
202424 | Former Community Centre |  | Former Community Centre, Angus Street, Lochee | 337561 | 731866 | 0.33905 | 2024-11-04 | Windfall | Consented (FULL) |  | 24/00703/FULL |  | Not yet started |  | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Short (1-3yrs) | Affordable | 0 | 8 | 0 | 8 | Deliverable |  | Abertay Housing Association | Abertay Housing Association | Brownfield | No | No
202426 | Commercial Street |  | 9 - 17 Commercial Street | 340546 | 730299 | 0.031011 | 2024-12-10 | Windfall | Consented (FULL) |  | 24/00752/FULL |  | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Short (1-3yrs) | Market | 4 | 0 | 4 | 0 | Deliverable |  | Sovereign Properties Stafford Ltd | Sovereign Properties Stafford Ltd | Brownfield | No | No

## Small site
Small Sites
HLA site reference | Site name | LDP reference | Site address | Easting | Northing | Site area (ha) | Year added to HLA | LDP/ Windfall/ Other | Planning status No consent Pending decision Consented (PPiP) Consented (Full) | Other detail Pre-application refused under appeal | Planning application(s) | Last approval date | Construction status Not yet started Started on site | Year construction started | Site capacity | Remaining capacity | Completions in audit year | Total completions | Pipeline timeframe Short (1-3 Yrs) Medium (4-6 Yrs) Long (7-10 Yrs) | Market/ Affordable/ Mixed | Number market | Number affordable | Number of flats | Number of houses | Deliverability status Deliverable, Deliverable with constraints, Constrained, Undeliverable, Removed | Action required Action Required To Support Delivery | Owner | Developer | Greenfield/ Brownfield | VDL | Self build | Dispute If the information provided within the HLA remains disputed and by who | Demolition Have list references where there was an application | Technician Notes
201410A | West Grove |  | 10 West Grove Avenue | 337465 | 730045 | 0.13055 | 2013-12-13 | Windfall | Consented (FULL) |  | 08/00592/FUL, 16/00314/FULL, 19/00376/FULL, 21/00671/FULL | 2022-03-04 | Started on site | 2020-12-18 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | Now PA 22/00491/FULL approved for STL
201607L | Colliongwood Crescent |  | Land to West of 20 Collingwood Crescent, Broughty Ferry | 347875 | 731329 | 0.040366 | 2015-05-15 | Windfall | Consented (FULL) |  | 15/00138/FULL, 19/00031/FULL | 2019-05-01 | Started on site | 2021-09-10 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | updated 24/25. Building work started but warrant expired 22/10/2023
201705B | Brook Street |  | 2/2, 197 Brook Street, Broughty Ferry | 346151 | 730939 | 0.033857 | 2010-04-08 | Windfall | Consented (FULL) |  | 10/00066/FULL, 13/00139FULL, 16/00488/FULL, 19/00185/FULL, 22/00283/FULL | 2022-06-02 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | BW extended
201705H | Monifieth Road |  | Garden Ground to South of 96 Monifieth Road | 347449 | 731179 | 0.057013 | 2016-09-14 | Windfall | Consented (FULL) |  | 16/00505/FULL | 2016-09-14 | Started on site | 2018-01-22 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change. BW expired - Notice of rejection 08/04/2020 & 15/10/2020. Applicant to submit time extension
201705K | Holly Hill |  | Holly Hill, 69 Dundee Road, Broughty Ferry | 344419 | 731195 | 0.18299 | 2016-12-08 | Windfall | Consented (FULL) |  | 16/00832/FULL, 19/00845/FULL, 22/00651/FULL | 2022-11-24 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
201805B | Monifieth Road |  | 92A Monifieth Road, Broughty Ferry | 347338 | 731179 | 0.10675 | 2017-05-12 | Windfall | Consented (FULL) |  | 16/00745/FULL | 2017-05-12 | Started on site | 2022-01-13 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | Works started. BW expired 23/08/24
201805G | Gibson Terrace |  | Land to the East of 3 Gibson Terrace | 341179 | 731912 | 0.13844 | 2017-10-26 | Windfall | Consented (FULL) |  | 17/00594/FULL, 20/00295/FULL | 2020-08-28 | Started on site | 2023-04-10 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | no change 24/25
201805J | Princes Street |  | 161 Princes Street | 341072 | 730954 | 0.038506 | 2017-11-15 | Windfall | Consented (FULL) |  | 17/00769/FULL | 2017-11-15 | Started on site | 2019-01-21 | 3 | 3 | 0 | 0 | Short (1-3yrs) | Market | 3 | 0 | 3 | 0 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | updated 24/25. Works started but BW & extensions expired.
202004P | Rockfield Crescent |  | Garden Ground to North of 7 Rockfield Crescent | 338252 | 730123 | 0.051985 | 2020-01-31 | Windfall | Consented (PPiP) |  | 19/00914/PPPL, 23/00511/PPPL | 2023-09-29 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | no change 24/25
202019D | Stonelee Guest House |  | Stonelee Guest House, 69 Monifieth Road, Broughty Ferry | 346866 | 731047 | 0.021311 | 2020-05-26 | Windfall | Consented (FULL) |  | 20/00148/FULL | 2020-05-26 | Started on site | 2021-10-11 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202031 | Pitkerro Mill |  | Pitkerro Mill, Kellas Road | 345088 | 733487 | 0.21123 | 2020-07-31 | Windfall | Consented (FULL) |  | 19/00861/FULL | 2020-07-31 | Started on site | 2023-08-14 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Deliverable |  | Harbyn Properties | Harbyn Properties | Brownfield | No | No |  |  | warrant extended till 19/10/2025
202032A | Symers Street |  | Land to the East of 6, Symers Street | 338543 | 734031 | 0.025906 | 2020-07-31 | Windfall | Consented (FULL) |  | 20/00232/FULL, 23/00474/FULL | 2023-09-29 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202035A | Bowling Green |  | Land to West of Bowling Green, Adelaide Place | 339508 | 731113 | 0.049833 | 2020-09-04 | Windfall | Consented (FULL) |  | 20/00310/PPPL, 23/00314/FULL | 2023-08-28 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | works started 09/04/25
202035C | Albany Road |  | Garden Ground to South of 50 Albany Road, Broughty Ferry | 344782 | 731333 | 0.13039 | 2020-10-02 | Windfall | Consented (PPiP) |  | 20/00289/PPPL, 23/00839/PPPL | 2024-02-02 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | no change 24/25
202035D | Springhill |  | 13 Springhill | 341571 | 731090 | 0.047011 | 2020-11-10 | Windfall | Consented (FULL) |  | 20/00459/FULL | 2020-11-10 | Started on site | 2021-01-01 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | no change 24/25
202035F | Dudhope Terrace |  | 9 Dudhope Terrace | 339435 | 730892 | 0.13097 | 2020-11-12 | Windfall | Consented (FULL) |  | 20/00548/FULL | 2020-11-12 | Started on site | 2021-05-09 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | Notice of Rejection x2 in 2023 & 1 in 2025
202035G | Victoria Chambers |  | G/1 Office, Victoria Chambers, 10 Victoria Road | 340214 | 730670 | 0.010618 | 2020-11-26 | Windfall | Consented (FULL) |  | 20/00133/FULL | 2020-11-26 | Started on site | 2021-12-13 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Tayside Property Management | Tayside Property Management | Brownfield | No | Single plot |  |  | no change 24/25
202035H | Murraygate |  | 1/0, 39 Murraygate | 340421 | 730459 | 0.018125 | 2020-12-11 | Windfall | Consented (FULL) |  | 20/00509/FULL | 2020-12-11 | Started on site | 2022-05-27 | 3 | 3 | 0 | 0 | Short (1-3yrs) | Market | 3 | 0 | 3 | 0 | Deliverable |  | Casa Fresa Holdings LLP | Casa Fresa Holdings LLP | Brownfield | No | No |  |  | temp cert refused 19/12/2024 for plots 1 & 2
202043 | Brown Street |  | Land to South of 75/77 Brown Street, Broughty Ferry | 346017 | 730834 | 0.012892 | 2020-11-06 | Windfall | Consented (FULL) |  | 20/00529/PPPL, 22/00547/FULL | 2022-11-18 | Started on site | 2025-02-17 | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 2 | 0 | Deliverable |  | Private | Private | Brownfield | No | No
202105C | Frederick Street |  | Garden Ground at 45 Frederick Street | 338778 | 733449 | 0.072435 | 2021-08-01 | Windfall | Consented (FULL) |  | 20/00721/FULL, 22/00756/FULL | 2023-02-08 | Started on site | 2024-07-23 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | updated 24/25
202105I | Strathern Road |  | 140 Strathern Road, Broughty Ferry | 345677 | 731472 | 0.11464 | 2021-08-01 | Windfall | Consented (FULL) |  | 20/00798/FULL | 2021-08-20 | Started on site | 2024-08-16 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  | 20/00798/FULL | updated 24/25
202208 | Forthill Road |  | 10 Forthill Road, Broughty Ferry | 346229 | 731308 | 0.041527 | 2022-03-16 | Windfall | Consented (PPiP) |  | 21/00688/PPPL | 2022-03-16 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | no change 24/25
202302 | Ellislea Road |  | Garden Ground at 9 Ellislea Road, Broughty Ferry | 345024 | 731414 | 0.10892 | 2022-08-23 | Windfall | Consented (FULL) |  | 22/00373/FULL | 2022-08-23 | Started on site | 2023-12-05 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | no change 24/25
202304 | Camphill Road |  | Land South of 65 Camphill Road, Broughty Ferry | 346894 | 731323 | 0.17794 | 2022-11-10 | Windfall | Consented (FULL) |  | 22/00545/FULL | 2022-11-10 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202305 | Balgillo Road |  | Land to South of 157 Balgillo Road, Broughty Ferry | 346450 | 732090 | 0.10384 | 2022-11-23 | Windfall | Consented (FULL) |  | 22/00503/FULL | 2022-11-23 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202306 | Lauderdale Avenue |  | Garden Ground to South of 88 Lauderdale Avenue | 338288 | 733486 | 0.03012 | 2022-11-25 | Windfall | Consented (PPiP) |  | 22/00535/PPPL | 2022-11-25 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202311 | Lochee Road |  | 142A Lochee Road | 338908 | 730689 | 0.020025 | 2023-03-08 | Windfall | Consented (FULL) |  | 22/00485/FULL | 2023-03-08 | Started on site | 2023-05-15 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25. CC rejected 30/10/2024
202313 | Mains of Gray Farm |  | Land to the South of Mains Of Gray Farm and West of Dykes Of Gray Road | 333577 | 732048 | 0.28448 | 2023-03-31 | Windfall | Consented (FULL) |  | 22/00818/FULL | 2023-03-31 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Greenfield | No | Single plot |  |  | No change 24/25. BW 23/00457/DOM2 withdrawn
202314 | Daniel Terrace |  | 2 Daniel Terrace | 339440 | 730204 | 0.033733 | 2023-05-18 | Windfall | Consented (FULL) |  | 23/00112/FULL | 2023-05-18 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 2 | 0 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | No change 24/25. Renewal of expired 18/00555/FULL
202315 | Broughty Ferry Road |  | 208 Broughty Ferry Road | 342298 | 731118 | 0.11554 | 2023-05-19 | Windfall | Consented (FULL) |  | 23/00128/FULL | 2023-05-19 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | No change 24/25. Sub-division of 1 house - 24/00599/DOM1 pending
202316 | Strathern Road |  | 32 Strathern Road, Broughty Ferry | 344271 | 731367 | 0.085898 | 2023-07-21 | Windfall | Consented (FULL) |  | 23/00199/FULL | 2023-07-21 | Started on site | 2024-04-19 | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202317 | Cleghorn Street |  | 25A Cleghorn Street | 338740 | 730664 | 0.0040554 | 2023-07-28 | Windfall | Consented (FULL) |  | 23/00279/FULL | 2023-07-28 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202318 | India Buildings |  | Upper Ground Floor, India Buildings, 86 Bell Street | 340211 | 730614 | 0.0077227 | 2023-07-31 | Windfall | Consented (FULL) |  | 23/00345/FULL | 2023-07-31 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Pavillion Properties | Pavillion Properties | Brownfield | No | Single plot |  |  | No BW 24/25
202321 | Kingsway |  | Garden Ground, 74 Kingsway | 340809 | 732504 | 0.031726 | 2023-08-10 | Windfall | Consented (PPiP) |  | 23/00110/PPPL, 24/00342/APCONL | 2024-07-23 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202323 | Nethergate |  | 32 Nethergate | 340252 | 730132 | 0.012693 | 2023-11-03 | Windfall | Consented (FULL) |  | 23/00587/FULL | 2023-11-03 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 2 | 0 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | No change 24/25. BW 24/00117/DOM4 PENDING
202326 | India Buildings |  | Unit 2, India Buildings, 86 Bell Street | 340204 | 730611 | 0.017497 | 2023-12-21 | Windfall | Consented (FULL) |  | 23/00694/FULL | 2023-12-21 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Pavillion Properties | Pavillion Properties | Brownfield | No | Single plot |  |  | No change 24/25
202402 | Bell Street |  | 46┬À& 50 Bell Street | 340141 | 730567 | 0.011603 | 2024-01-12 | Windfall | Consented (FULL) |  | 23/00701/FULL | 2024-01-12 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25. BW 24/00295/DOM1 pending
202403 | Stephens Yard |  | Land South Of Stephens Yard, Shepherds Loan | 338788 | 729671 | 0.050142 | 2024-01-23 | Windfall | Consented (FULL) |  | 23/00170/FULL | 2024-01-23 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Market | 2 | 0 | 0 | 2 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | No change 24/25
202404 | Perth Road |  | Garden Ground East Of 381 Perth Road | 336752 | 730030 | 0.31682 | 2024-02-05 | Windfall | Consented (FULL) |  | 23/00668/FULL | 2024-02-05 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202405 | India Buildings |  | Unit 1, India Buildings, 86 Bell Street | 340205 | 730599 | 0.012526 | 2024-02-29 | Windfall | Consented (FULL) |  | 23/00855/FULL | 2024-02-29 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25
202406 | Gotterstone Drive |  | Land East Of 61 Gotterstone Drive | 344544 | 731906 | 0.035516 | 2024-03-15 | Windfall | Consented (FULL) |  | 23/00079/FULL | 2024-03-15 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | No change 24/25. 25/00047/DOM2 pending
202407 | Woodcroft |  | Land To West Of Woodcroft, Dundee Road, Broughty Ferry | 344360 | 731160 | 0.13338 | 2024-03-20 | Windfall | Consented (FULL) |  | 23/00404/FULL | 2024-03-20 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Greenfield | No | Single plot |  |  | No change 24/25
202409 | Liff Road |  | 52 Liff Road | 337542 | 731818 | 0.0034755 | 2024-04-09 | Windfall | Consented (FULL) |  | 24/00239/FULL | 2024-06-26 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | New site 24/25. No BW yet
202410 | Hillbank Road |  | 1 Hillbank Road | 340583 | 731366 | 0.043539 | 2024-04-17 | Windfall | Consented (FULL) |  | 24/00103/FULL | 2024-04-17 | Not yet started |  | 2 | 2 | 0 | 0 | Short (1-3yrs) | Affordable | 0 | 2 | 2 | 0 | Deliverable |  | Hillcrest Homes (Scotland) Ltd |  | Brownfield | No | No |  |  | New site 24/25. Sub-division of 1 flat into 2.
202413 | King Street |  | 421 King Street, Broughty Ferry | 346578 | 730656 | 0.036566 | 2024-06-21 | Windfall | Consented (FULL) |  | 24/00427/FULL | 2024-09-04 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  | 24/00428/CON, 24/00511/DOM4 | New site 24/25. BW for demolition of existing house.
202417 | Cleghorn Street |  | 36 - 38 Cleghorn Street | 338788 | 730722 | 0.005934 | 2024-08-12 | Windfall | Consented (FULL) |  | 24/00506/FULL | 2024-10-08 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | Single plot |  |  | New site 24/25.
202422 | Belsize House |  | Belsize House, Belsize Road | 344010 | 731255 | 0.21587 | 2024-09-19 | Windfall | Consented (FULL) |  | 24/00560/FULL | 2024-12-04 | Not yet started |  | 3 | 3 | 0 | 0 | Short (1-3yrs) | Market | 3 | 0 | 0 | 3 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | New site 24/25, BW 24/00593/DOM1 pending
202429 | Myrekirk Road |  | Garden Ground North Of 5 Myrekirk Road | 335459 | 731606 | 0.045775 | 2024-12-11 | Windfall | Consented (FULL) |  | 24/00777/FULL |  | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | New site 24/25. No BW yet
202430 | Scrimgeours Building |  | 4/1 Scrimgeours Building, 4 Whitehall Street | 340278 | 730164 | 0.007475 | 2024-12-18 | Windfall | Consented (FULL) |  | 24/00804/FULL | 2025-03-10 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Private | Private | Brownfield | No | No |  |  | New site 24/25. BW Pending
202501 | Arbroath Road |  | 105 Arbroath Road | 341561 | 731147 | 0.012721 | 2025-01-23 | Windfall | Consented (FULL) |  | 22/00696/FULL, 24/00788/FULL | 2025-03-13 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 1 | 0 | Deliverable |  | Alex Sikorsky AK Property Ltd | Alex Sikorsky AK Property Ltd | Brownfield | No | No |  |  | New site 24/25
202502 | Clovis Duveau Drive |  | Land To East Of 15 Clovis Duveau Drive | 335515 | 730237 | 0.051964 | 2025-01-30 | Windfall | Consented (FULL) |  | 21/00423/FULL, 24/00053/FULL, 24/00802/FULL | 2024-05-27 | Not yet started |  | 1 | 1 | 0 | 0 | Short (1-3yrs) | Market | 1 | 0 | 0 | 1 | Deliverable |  | Private | Private | Greenfield | No | Single plot |  |  | New site 24/25. Previous planning permission given in 2022. BW pending

## Removed
Removed Sites
Completed sites
HLA site reference | Site name | LDP reference | Site address | Easting | Northing | Site area (ha) | Year added to HLA | LDP/ Windfall/ Other | Planning status No consent Pending decision Consented (PPiP) Consented (Full) | Other detail Pre-application refused under appeal | Planning application(s) | Last approval date | Construction status Not yet started Started on site | Year construction started | Site capacity | Remaining capacity | Completions in audit year | Total completions | Pipeline timeframe Short (1-3 Yrs) Medium (4-6 Yrs) Long (7-10 Yrs) | Market/ Affordable/ Mixed | Number market | Number affordable | Number of flats | Number of houses | Deliverability status Deliverable, Deliverable with constraints, Constrained, Undeliverable, Removed | Action required Action Required To Support Delivery | Owner | Developer | Greenfield/ Brownfield | VDL | Self build cannot determine self build. Have marked where it's a single plot | Dispute If the information provided within the HLA remains disputed and by who | Demolition Have list references where there was an application
200504D | Aberlady Crescent Phase 3B/4 | H32 | Land at Aberlady Crescent | 343953 | 733534 | 1.8237 | 2020-10-22 | LDP | Consented (FULL) |  | 20/00121/FULL, 22/00657/FULL | 2023-02-10 | Started on site | 2019-01-10 | 32 | 0 | 2 | 32 | Short (1-3yrs) | Market | 0 | 0 | 0 | 32 | Removed |  | DJ Laing | DJ Laing | Brownfield | No | No
200911 | Former MacAlpine Primary School | H08 | St Leonard Place | 338134 | 733812 | 1.5846 | 2019-06-24 | LDP | Consented (FULL) |  | 17/00420/FULL, 21/00406/FULL | 2021-12-15 | Started on site | 2020-11-06 | 33 | 0 | 1 | 33 |  | Market | 0 | 0 | 0 | 33 | Removed |  | H & H Properties | H & H Properties | Brownfield | No | No
201108 | Former Derby Street Multis |  | Site Of Bucklemaker and Butterburn Courts, Strathmartine Road | 339832 | 731556 | 3.587 | 2011-04-01 | Windfall | Consented (FULL) |  | 16/00806/FULM, 17/00799/FULL | 2017-12-11 | Started on site | 2018-06-20 | 162 | 0 | 26 | 162 | Short (1-3yrs) | Affordable | 0 | 0 | 123 | 39 | Removed |  | DCC/Hillcrest |  | Brownfield | No | No |  | 12/00199/DEMOL
201410C | Bughties Road |  | 22 Bughties Road, Broughty Ferry | 347058 | 731241 | 0.086026 | 2017-01-05 | Windfall | Consented (FULL) |  | 16/00889/FULL, 19/00822/FULL | 2020-01-13 | Started on site | 2019-08-08 | 1 | 0 | 1 | 1 | Short (1-3yrs) | Market | 0 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
201415 | Former St Columbas Primary School | H12 | Kirkton Road | 339075 | 733403 | 0.66612 | 2014-04-01 | LDP | Consented (FULL) |  | 17/00417/FULL | 2020-11-18 | Started on site | 2023-09-15 | 21 | 0 | 8 | 21 | Short (1-3yrs) | Market | 0 | 0 | 0 | 21 | Removed |  | H & H Properties | H & H Properties | Brownfield | No | No
201506 | Falkland Crescent |  | Land North of Falkland Crescent | 347459 | 732285 | 0.10851 | 2007-11-06 | Windfall | Consented (FULL) | Under Appeal | 07/00097/FUL | 2007-11-06 | Started on site |  | 1 | 0 | 1 | 1 | Short (1-3yrs) | Market | 0 | 0 |  | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
201510B | Burnside Street | H06 | Site of 6-10 Burnside Street | 337951 | 731543 | 0.041787 | 2023-05-04 | LDP | Consented (FULL) |  | 22/00748/FULL | 2023-05-04 | Started on site | 2023-07-03 | 2 | 0 | 2 | 2 | Short (1-3yrs) | Market | 0 | 0 | 0 | 2 | Removed |  | Private | Private | Brownfield | No | No
201824A | Ballumbie Road Phase 1 | H45 | Land East of Ballumbie Road, Phase 1 | 344610 | 733827 | 3.7657 | 2019-09-25 | LDP | Consented (FULL) |  | 19/00128/FULM | 2019-09-25 | Started on site | 2020-01-22 | 76 | 0 | 1 | 76 | Short (1-3yrs) | Market | 0 | 0 | 0 | 76 | Removed |  | Stewart Milne Homes | Stewart Milne Homes | Greenfield | No | No
201826D | Summerfield Avenue | H29 | Land to West Of Summerfield Avenue at Summerfield Gardens | 343680 | 733153 | 0.36088 | 2023-03-30 | LDP | Consented (FULL) |  | 22/00148/FULL | 2023-03-30 | Started on site | 2023-04-03 | 8 | 0 | 8 | 8 | Short (1-3yrs) | Market | 0 | 0 | 0 | 8 | Removed |  | Invertay Homes Ltd | Invertay Homes Ltd | Brownfield |  | No
201902 | Coldside Road |  | Land to South of Coldside Road and West of Strathmartine Road | 339507 | 731945 | 0.85219 | 2018-07-16 | Windfall | Consented (FULL) |  | 17/00933/FULL | 2018-07-16 | Started on site | 2021-11-22 | 30 | 0 | 10 | 30 | Short (1-3yrs) | Affordable | 0 | 0 | 12 | 18 | Removed |  | Caledonia HA | GMC Ventures Ltd | Brownfield |  | No
201913 | Candle Lane |  | Car Park, 9 - 11 Candle Lane | 340603 | 730389 | 0.18826 | 2018-06-21 | Windfall | Consented (FULL) |  | 18/00016/FULL | 2018-06-21 | Started on site | 2019-09-20 | 24 | 0 | 24 | 24 | Short (1-3yrs) | Affordable | 0 | 0 | 24 | 0 | Removed |  | Hillcrest HA | Hillcrest HA | Brownfield |  | No
202003 | Murraygate |  | 11-23 Murraygate | 340422 | 730416 | 0.068309 | 2019-04-17 | Windfall | Consented (FULL) |  | 18/01012/FULL | 2019-04-17 | Started on site | 2021-06-25 | 31 | 0 | 31 | 31 | Short (1-3yrs) | Affordable | 0 | 0 | 31 | 0 | Removed |  | Hillcrest HA | West Ranga (Dundee) Ltd | Brownfield | No | No
202022 | Downfield House |  | Downfield House, East School Road | 339035 | 733033 | 0.31929 | 2020-05-01 | Windfall | Consented (FULL) |  | 19/00830/FULL, 22/0024/NMV | 2020-05-01 | Started on site | 2022-05-30 | 14 | 0 | 10 | 14 | Short (1-3yrs) | Market | 0 | 0 | 12 | 2 | Removed |  | Aberkell Developments | Aberkell Developments | Brownfield | No | No
202032B | Fairfield Road |  | 10 Fairfield Road, Broughty Ferry | 344602 | 731449 | 0.20792 | 2020-09-01 | Windfall | Consented (FULL) |  | 20/00160/FULL, 21/00651/FULL, | 2021-11-11 | Started on site | 2022-10-01 | 4 | 0 | 3 | 4 | Short (1-3yrs) | Market | 0 | 0 | 4 | 0 | Removed |  | West Developments (Scotland) Ltd | West Developments (Scotland) Ltd | Brownfield | No | No
202035K | Caelochan Road |  | Garden Ground to North of 4 Caenlochan Road | 345098 | 731659 | 0.11504 | 2021-02-10 | Windfall | Consented (FULL) |  | 20/00625/FULL | 2021-02-10 | Started on site | 2023-12-11 | 1 | 0 | 1 | 1 | Short (1-3yrs) | Market | 0 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
202061D | Nethergate |  | Basement, 138 Nethergate | 340057 | 729953 | 0.012799 | 2020-08-11 | Windfall | Consented (FULL) |  | 20/00343/FULL | 2020-08-11 | Started on site | 2023-08-10 | 1 | 0 | 1 | 1 |  | Market | 0 | 0 | 1 | 0 | Removed |  | Private | Private | Brownfield | No | Single plot
202066 | Sites 1 & 2 |  | Land East and West of Liff Place and North of Brownhill Place | 336499 | 732119 | 0.65834 | 2020-12-17 | Windfall | Consented (FULL) |  | 20/00247/FULL | 2020-12-17 | Started on site | 2023-01-16 | 23 | 0 | 23 | 23 | Short (1-3yrs) | Affordable | 0 | 0 | 20 | 3 | Removed |  | Blackwood Group | Campion Homes Limited | Brownfield | No | No
202067 | Sites 3 & 4 |  | Land at Gourdie Place, Gourdie Crescent, Charleston Road, Invercraig Place and Balgarthno Road | 336236 | 731913 | 0.91009 | 2020-12-17 | Windfall | Consented (FULL) |  | 20/00248/FULL | 2020-12-17 | Started on site | 2023-01-16 | 22 | 0 | 22 | 22 | Short (1-3yrs) | Affordable | 0 | 0 | 12 | 10 | Removed |  | Blackwood Homes | Campion Homes Limited | Brownfield |  | No
202068 | Sites 5 & 6 |  | Land to South of Buttars Road | 336603 | 731958 | 0.48089 | 2020-12-17 | Windfall | Consented (FULL) |  | 20/00249/FULL | 2020-12-17 | Started on site | 2023-01-16 | 9 | 0 | 9 | 9 | Short (1-3yrs) | Affordable | 0 | 0 | 6 | 3 | Removed |  | Blackwood Homes | Campion Homes Ltd | Brownfield |  | No
202206 | Site 7 |  | Land East and West of Liff Place and North of Brownhill Place | 336681 | 732054 | 0.29665 | 2021-05-21 | Windfall | Consented (FULL) |  | 20/00250/FULL | 2021-05-21 | Started on site | 2023-01-16 | 12 | 0 | 12 | 12 | Short (1-3yrs) | Affordable | 0 | 0 | 12 | 0 | Removed |  | Blackwood Homes | Campion Homes | Brownfield |  | No
202209 | The White House |  | The White House, 126 Brown Street, Broughty Ferry | 346062 | 730895 | 0.012421 | 2022-08-04 | Windfall | Consented (FULL) |  | 22/00357/FULL | 2022-08-04 | Started on site | 2024-01-29 | 1 | 0 | 1 | 1 | Short (1-3yrs) | Market | 0 | 0 | 1 | 0 | Removed |  |  |  | Brownfield
202210 | 22 Springfield |  | 22 Springfield | 339364 | 729850 | 0.052131 | 2022-09-23 | Windfall | Consented (FULL) |  | 22/00392/FULL | 2022-09-23 | Started on site | 2023-03-30 | 2 | 0 | 2 | 2 | Short (1-3yrs) | Market | 0 | 0 | 0 | 2 | Removed |  | Private | Private | Brownfield | No | No
202325 | India Buildings |  | Upper Ground Floor, Unit 2, India Buildings, 86 Bell Street | 340216 | 730603 | 0.014148 | 2023-11-23 | Windfall | Consented (FULL) |  | 23/00571/FULL | 2023-11-23 | Started on site | 2024-07-01 | 1 | 0 | 1 | 1 |  | Market | 0 | 0 | 1 | 0 | Removed |  | Pavillion Properties | Pavillion Properties | Brownfield | No | Single plot
202327 | India Buildings |  | Unit 2, India Buildings, 86 Bell Street | 340216 | 730603 | 0.014137 | 2023-12-21 | Windfall | Consented (FULL) |  | 23/00574/FULL | 2023-12-21 | Started on site |  | 1 | 0 | 1 | 1 | Short (1-3yrs) | Market | 0 | 0 | 1 | 0 | Removed |  | Pavilion Properties | Pavilion Properties | Brownfield | No | Single plot
Expired sites
HLA site reference | Site name | LDP reference | Site address | Easting | Northing | Site area (ha) | Year added to HLA | LDP/ Windfall/ Other | Planning status No consent Pending decision Consented (PPiP) Consented (Full) | Other detail Pre-application refused under appeal | Planning application(s) | Last approval date | Construction status Not yet started Started on site | Year construction started | Site capacity | Remaining capacity | Completions in audit year | Total completions | Pipeline timeframe Short (1-3 Yrs) Medium (4-6 Yrs) Long (7-10 Yrs) | Market/ Affordable/ Mixed To be updated by LS/RP? | Number market To be updated by LS/RP? | Number affordable To be updated by LS/RP? | Number of flats | Number of houses | Deliverability status Deliverable, Deliverable with constraints, Constrained, Undeliverable, Removed | Action required Action Required To Support Delivery | Owner To be checked LS/RP | Developer To be checked LS/RP | Greenfield/ Brownfield | VDL | Self build cannot determine self build. Have marked where it's a single plot | Dispute If the information provided within the HLA remains disputed and by who | Demolition Have list references where there was an application
201805C | Glamis Road |  | 28A Glamis Road | 336991 | 730301 | 0.040016 | 2017-05-24 | Windfall | Consented (FULL) |  | 17/00266/FULL, 21/00451/FULL | 2021-08-19 | Not yet started |  | 1 | 1 | 0 | 0 |  | Market | 1 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
201805D | Harefield Road |  | Land To The East Of 16 Harefield Road | 338201 | 731821 | 0.15268 | 2017-06-01 | Windfall | Consented (FULL) |  | 17/00247/FULL, 22/00010/FULL | 2022-03-10 | Not yet started |  | 1 | 2 | 0 | 0 |  | Market | 2 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
201805M | North Grange Farm |  | Land To West Of Livery Stable, North Grange Farm, Arbroath Road | 348337 | 733354 | 0.18637 | 2018-03-26 | Windfall | Consented (FULL) |  | 18/00053/FULL, 21/00123/FULL | 2021-05-07 | Not yet started |  | 1 | 1 | 0 | 0 |  | Market | 1 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot |  | 21/00123/FULL incl demolition
202061F | Americanmuir Road |  | Garden Ground at 38 Americanmuir Road | 338540 | 733383 | 0.13032 | 2021-05-12 | Windfall | Consented (FULL) |  | 20/00690/FULL | 2021-05-12 | Not yet started |  | 1 | 1 | 0 | 0 |  | Market | 1 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
202105B | Springfield |  | G/0, 8 Springfield | 339325 | 729829 | 0.022691 | 2021-07-01 | Windfall | Consented (FULL) |  | 20/00618/FULL | 2021-07-16 | Not yet started |  | 2 | 2 | 0 | 0 |  | Market | 2 | 0 | 2 | 0 | Removed |  | Private | Private | Brownfield | No | No
202105D | North Street |  | 40 North Street | 339958 | 731642 | 0.021458 | 2021-10-01 | Windfall | Consented (FULL) |  | 21/00008/FULL | 2021-10-21 | Not yet started |  | 1 | 1 | 0 | 0 |  | Market | 1 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot
202105F | MF Space, Reform Street |  | MF Space, 2/2, 51 Reform Street | 340245 | 730375 | 0.010331 | 2021-11-01 | Windfall | Consented (FULL) |  | 21/00719/FULL | 2021-11-18 | Not yet started |  | 4 | 4 | 0 | 0 | Short (1-3yrs) | Market | 4 | 0 | 4 | 0 | Removed |  | Private | Private | Brownfield | No | No
202105G | Cafe, Reform Street |  | Cafe, 2/2, 51 Reform Street | 340245 | 730375 | 0.010331 | 2021-08-21 | Windfall | Consented (FULL) |  | 21/00501/FULL | 2021-08-27 | Not yet started |  | 1 | 1 | 0 | 0 |  | Market | 1 | 0 | 1 | 0 | Removed |  | Private | Private | Brownfield | No | Single plot
202105J | Balgowan Drive |  | 7 Balgowan Drive | 339134 | 733842 | 0.056125 | 2021-08-01 | Windfall | Consented (FULL) |  | 21/00471/FULL | 2021-08-17 | Not yet started |  | 1 | 1 | 0 | 0 |  | Market | 1 | 0 | 0 | 1 | Removed |  | Private | Private | Brownfield | No | Single plot |  | 19/00536/DOM4
202107 | Fernbrae Hospital |  | Fernbrae Hospital, 329 Perth Road | 337615 | 729923 | 1.1481 | 2021-12-01 | Windfall | Consented (FULL) |  | 21/00604/FULL | 2021-12-15 | Not yet started |  | 22 | 22 | 0 | 0 | Short (1-3yrs) | Market | 22 | 0 | 17 | 5 | Removed |  | Private | Private | Brownfield | No | No
202201 | Blackness Road |  | Land to East of 247 Blackness Road | 338564 | 730306 | 0.1765 | 2022-02-09 | Windfall | Consented (FULL) |  | 21/00525/FULL, 25/00063/FULL | 2022-02-09 | Not yet started |  | 24 | 24 | 0 | 0 | Short (1-3yrs) | Affordable | 0 | 24 | 24 | 0 | Removed |  | Dundee City Council | Dundee City Council | Brownfield | No | No
202203 | Nicoll Street |  | Meeting Hall, 6 Nicoll Street | 339986 | 730411 | 0.039053 | 2022-03-17 | Windfall | Consented (FULL) |  | 20/00598/FULL | 2022-03-17 | Not yet started |  | 10 | 10 | 0 | 0 | Short (1-3yrs) | Market | 10 | 0 | 10 | 0 | Removed |  | Private | Private | Brownfield | No | No

## Constrained
Constrained Sites
HLA site reference | Site name | LDP reference | Site address | Easting | Northing | Site area (ha) | Year added to HLA | LDP/ Windfall/ Other | Planning status No consent Pending decision Consented (PPiP) Consented (Full) | Other detail Pre-application refused under appeal | Planning application(s) | Last approval date | Construction status Not yet started Started on site | Year construction started | Site capacity | Remaining capacity | Completions in audit year | Total completions | Pipeline timeframe Short (1-3 Yrs) Medium (4-6 Yrs) Long (7-10 Yrs) | Market/ Affordable/ Mixed | Number market | Number affordable | Number of flats | Number of houses | Deliverability status Deliverable, Deliverable with constraints, Constrained, Undeliverable, Removed | Action required Action Required To Support Delivery | Owner | Developer | Greenfield/ Brownfield | VDL | Self build | Dispute If the information provided within the HLA remains disputed and by who | Demolition Have list references where there was an application
200321 | Queen Victoria Works | H13 | Brook Street, Dundee | 339248 | 730423 | 1.2498 | 2003-04-01 | LDP | No consent |  |  |  | Not yet started |  | 50 | 50 | 0 | 0 | 10+Yrs | Market | 50 | 0 | 0 | 50 | Constrained |  | Private | Private | Brownfield | Yes | No
200353 | Lothian Crescent | H26 | Lothian Crescent | 343118 | 733510 | 0.83453 | 2003-04-01 | LDP | No consent |  |  |  | Not yet started |  | 15 | 15 | 0 | 0 |  | Affordable | 0 | 15 | 0 | 0 | Constrained |  |  |  | Brownfield | Yes | No
200728 | Princes Street | H18 | Princes Street | 340941 | 730852 | 0.25972 | 2007-04-01 | LDP | No consent | Pre-application | PREAPP/001/2019 |  | Not yet started |  | 20 | 20 | 0 | 0 | 10+Yrs | Market | 20 | 0 | 0 | 0 | Constrained |  | Dundee City Council |  | Brownfield | No | No
200807 | Quarry Gardens | H04 | Land at Quarry Gardens | 337130 | 732089 | 0.44319 | 2008-04-01 | LDP | No consent |  |  |  | Not yet started |  | 18 | 18 | 0 | 0 |  | Market | 18 | 0 | 0 | 0 | Constrained |  |  |  | Brownfield | Yes | No
201205 | Earn Crescent | H02 | Land at Earn Crescent | 336292 | 730903 | 0.56489 | 2012-04-01 | LDP | No consent |  |  |  | Not yet started |  | 20 | 20 | 0 | 0 | 10+Yrs | Market | 20 | 0 | 0 | 0 | Constrained |  | Dundee City Council |  | Brownfield | No | No
201220 | MOM Phase 4 | H19 | Land at Barns Of Claverhouse Road | 340911 | 733631 | 0.41142 | 2012-04-01 | LDP | No consent |  |  |  | Not yet started |  | 12 | 12 | 0 | 0 |  | Market | 12 | 0 | 0 | 0 | Constrained |  |  |  | Brownfield | No | No
201413 | Clatto Reservoir | H03 | Land To South Of Clatto Reservoir, Dalmahoy Drive | 336967 | 734365 | 3.4021 | 2014-04-01 | LDP | No consent |  |  |  | Not yet started |  | 60 | 60 | 0 | 0 | Medium (4-6Yrs) | Market | 60 | 0 | 0 | 0 | Constrained |  | Scottish Water |  | Brownfield | No | No
201424 | Strathyre Avenue | H47 | Land To East Of Strathyre Avenue, Broughty Ferry | 347040 | 732767 | 1.5713 | 2014-04-01 | LDP | No consent |  |  |  | Not yet started |  | 26 | 26 | 0 | 0 |  | Market | 26 | 0 | 0 | 0 | Constrained |  | Private | Private | Greenfield | No | No
201509 | Linlathen House |  | Land To East Of Nursing Home, Linlathen Road | 346406 | 732975 | 1.5242 | 2015-04-01 | Windfall | Consented (FULL) |  | 10/00298/FULM |  | Started on site |  | 60 | 42 | 0 | 18 | 10+Yrs | Market | 42 | 0 | 0 | 0 | Constrained |  | Private | Private | Greenfield | No | No