## Effective Greenfield 22-23
Effective Greenfield 2022/23
[12 empty] | Short Term |  |  | Medium Term |  |  | Long Term
HLA Ref | LDP 2019 Ref | Date Added | Site | Owner / Developer | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Complete 22/23 | Units to build | Tenure Type | year 23/24 | year 24/25 | year 25/26 | year 26/27 | year 27/28 | year 28/29 | year 29/30 | year 30/31 | year 31/32 | year 32/33 | Later Years | Totals
200356A |  | 2016-03-11 | WESTERN GATEWAY, SOUTH GRAY | SPRINGFIELD | 19.3417 | 2018-11-06 | Under Construction | 341 | 7 | 139 | Private | 0 | 45 | 45 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139
200408 |  | 2015-06-03 | WESTERN GATEWAY, SWALLOW | SPRINGFIELD | 24.3312 | 2017-07-19 | Under Construction | 230 | 0 | 129 | Private | 33 | 41 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 129
200738 |  | 2016-06-17 | DUNDEE WESTERN LIFF PHASE 2 | SPRINGFIELD | 7.8207 | 2019-02-06 | Under Construction | 100 | 0 | 100 | Private | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 100
201423 |  | 2016-07-20 | PITKERRO MILL | SOUTH TAY LTD | 1.0007 | 2016-07-20 | Under Construction | 6 | 0 | 6 | Private | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
201821 | H42 | 2018-04-01 | WESTERN GATEWAY, LIFF | NHS | 3.2797 |  | Allocated in LDP | 30 | 0 | 30 | Private | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 30
201822 | H43 | 2018-04-01 | DYKES OF GRAY, NORTH EAST | SPRINGFIELD | 13.4423 |  | Allocated in LDP | 215 | 0 | 215 | Private | 0 | 0 | 12 | 24 | 30 | 30 | 39 | 40 | 40 | 0 | 0 | 215
201823 | H44 | 2018-04-01 | BALDRAGON FARM | AVANT HOMES | 6.2216 | 2021-04-09 | Under Construction | 120 | 31 | 89 | Private | 30 | 30 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89
201824B | H45 | 2021-05-21 | BALLUMBIE ROAD, LAND TO EAST OF - PHASE 2 | STEWART MILNE | 7.4158 | 2021-05-21 | Detailed Planning Consent | 150 | 0 | 150 | Private | 18 | 36 | 36 | 36 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 150
201829 | H41 | 2018-01-11 | DYKES OF GRAY, NORTH WEST | SPRINGFIELD | 21.9833 |  | Allocated in LDP | 250 | 0 | 250 | Private | 0 | 0 | 0 | 0 | 44 | 41 | 50 | 50 | 65 | 0 | 0 | 250
201830 | H46 | 2018-06-25 | ARBROATH ROAD, LINLATHEN | KIRKWOOD HOMES | 15.8973 | 2021-07-01 | Under Construction | 250 | 64 | 102 | Private | 42 | 43 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102
Totals | [7 empty] | 1692 | 102 | 1210 |  | 129 | 220 | 164 | 134 | 123 | 156 | 89 | 90 | 105 | 0 | 0 | 1210

## Effective Brownfield 22-23
Effective Brownfield 2022/23
[12 empty] | Short Term |  |  | Medium Term |  |  | Long Term
HLA Ref | LDP 2019 Ref | Date Added | Site | Owner / Developer | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Complete 22/23 | Units to build | Tenure Type | year 23/24 | year 24/25 | year 25/26 | year 26/27 | year 27/28 | year 28/29 | year 29/30 | year 30/31 | year 31/32 | year 32/33 | Later Years | Totals
200347 |  | 2013-12-17 | MONIFIETH ROAD, ARMITSTEAD | H & H PROPERTIES LTD | 1.1412 | 2022-04-15 | Under Construction | 26 | 0 | 26 | Private | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
200504D | H32 | 2020-10-22 | ABERLADY CRESCENT PHASE 3B/4 | DJ LAING | 1.7729 | 2023-02-10 | Under Construction | 34 | 22 | 7 | Private | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
200611 |  | 2007-06-05 | RIVERSIDE DRIVE, FORMER HOMEBASE SITE | H & H PROPERTIES LTD | 1.6776 | 2007-06-05 | Under Construction | 134 | 4 | 50 | Private | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
200909 | H11 | 2009-04-01 | EAST SCHOOL ROAD, FORMER DOWNFIELD PS | H & H PROPERTIES LTD | 1.2778 | 2020-11-18 | Detailed Planning Consent | 23 | 0 | 23 | Private | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
200911 | H08 | 2019-06-24 | ST LEONARD PLACE, FORMER MACALPINE PS | H & H PROPERTIES LTD | 1.5846 | 2021-12-15 | Under Construction | 33 | 16 | 13 | Private | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
200913 | H09 | 2009-04-01 | RANNOCH ROAD, FORMER LAWSIDE ACADEMY | DUNDEE CITY COUNCIL | 4.0249 |  | Allocated in LDP | 70 | 0 | 70 | Private | 0 | 0 | 20 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 70
201008 | H31 | 2010-04-01 | LOTHIAN CRESCENT, BOWLING GREEN EAST | DUNDEE CITY COUNCIL | 1.3369 |  | Allocated in LDP | 30 | 0 | 30 | Private | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201009A | H30 | 2018-11-15 | HADDINGTON AVENUE (Phase 1) | MERCHANT/HOME SCOTLAND | 0.47446 | 2019-09-19 | Under Construction | 13 | 10 | 3 | Private | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
201010 | H28 | 2010-04-01 | TRANENT GROVE | DISCOVERY HOMES LTD | 3.7588 | 2022-12-16 | Allocated in LDP | 53 | 0 | 53 | Private | 0 | 0 | 0 | 22 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 53
201010A | H28 | 2022-12-16 | TRANENT GROVE | DISCOVERY HOMES LTD | 1.3428 | 2022-12-16 | Detailed Planning Consent | 17 | 0 | 17 | Private | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
201011 | H27 | 2010-04-01 | WHITFIELD DRIVE, FORMER WHITFIELD PS | GEORGE MARTIN/ANGUS HA | 1.9216 |  | Allocated in LDP | 25 | 0 | 25 | Private/RSL | 0 | 18 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
201012 | H25 | 2010-04-01 | LOTHIAN CRESCENT, FORMER WHITFIELD SHOPPING CENTRE | DUNDEE CITY COUNCIL | 1.8274 |  | Allocated in LDP | 30 | 0 | 30 | Private/RSL | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201102 |  | 2010-12-21 | DURA STREET, 3 | WHITTET LTD | 0.07577 | 2023-06-29 | Detailed Planning Consent | 8 | 0 | 8 | Private | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
201106 |  | 2011-04-01 | SEAGATE/TRADES LANE | HILLCREST HA | 0.035264 | 2017-08-21 | Under Construction | 28 | 0 | 28 | RSL | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
201108 |  | 2011-04-01 | DERBY STREET, FORMER MULTIS | DCC/HILLCREST | 3.5872 | 2017-12-11 | Under Construction | 163 | 26 | 137 | DCC/RSL | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137
201109 | H17 | 2011-04-01 | CENTRAL WATERFRONT | DUNDEE CITY COUNCIL | 23.9694 | 2020-10-16 | Allocated in LDP | 276 | 0 | 276 | Mixed | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 70 | 70 | 76 | 0 | 276
201109A | H17 | 2017-06-23 | CENTRAL WATERFRONT - SITE 6 | DUNDEE CITY COUNCIL | 0.72316 | 2018-08-17 | Not Started | 99 | 0 | 99 | Private | 0 | 0 | 0 | 0 | 50 | 49 | 0 | 0 | 0 | 0 | 0 | 99
201109B | H17 | 2020-10-16 | DOCK STREET, HARBOUR CHAMBERS / CUSTOMS HOUSE | ALICYDON LTD | 0.37882 | 2020-10-16 | Under Construction | 49 | 0 | 49 | Private | 0 | 0 | 0 | 20 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 49
201110 | H23 | 2011-04-01 | BALLOCHMYLE DRIVE, FORMER MOSSGIEL PSC PHASE 2 | ABERTAY HA | 1.4577 |  | Allocated in LDP | 30 | 0 | 30 | RSL | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201213 | H22 | 2012-04-01 | HEBRIDES DRIVE SOUTH EAST, MOM-PHASE 4) | HOME SCOTLAND | 0.57888 | 2019-04-16 | Allocated in LDP | 20 | 0 | 20 | RSL | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
201214 | H21 | 2012-04-01 | HEBRIDES DRIVE NORTH EAST, MOM-PHASE 4 | HOME SCOTLAND | 0.4467 | 2019-04-16 | Allocated in LDP | 15 | 0 | 15 | RSL | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
201221 | H20 | 2012-04-01 | HEBRIDES DRIVE WEST, MOM-PHASE 4 | DUNDEE CITY COUNCIL | 0.63833 |  | Allocated in LDP | 10 | 0 | 10 | Private | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10
201303 |  | 2013-04-01 | PITKERRO ROAD, 189-197 | HOME SCOTLAND | 1.2203 | 2021-06-09 | Under Construction | 29 | 0 | 29 | RSL | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
201413 | H03 | 2014-04-01 | CLATTO, LAND AT | SCOTTISH WATER | 3.4021 |  | Allocated in LDP | 60 | 0 | 60 | Private | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 60
201414 | H10 | 2014-04-01 | LAUDERDALE AVENUE | INVERTAY HOMES | 0.82733 | 2018-09-14 | Under Construction | 27 | 12 | 4 | Private | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
201415 | H12 | 2014-04-01 | KIRKTON ROAD, FORMER ST COLUMBAS PS | H & H PROPERTIES LTD / DCC | 0.66612 | 2020-11-18 | Allocated in LDP | 21 | 0 | 21 | Private | 0 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
201417 | H05 | 2014-04-01 | SOUTH ROAD, FORMER LOCHEE PS | DUNDEE CITY COUNCIL | 1.7822 |  | Allocated in LDP | 30 | 0 | 30 | Private | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201510 | H06 | 2015-04-01 | LOCHEE DISTRICT CENTRE | HILLCREST HA | 6.1424 | 2020-01-27 | Under Construction | 40 | 0 | 40 | RSL | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
201601 |  | 2015-07-28 | GARDYNE ROAD, WINNOCKS, 1 | PRIVATE | 0.19663 | 2018-02-08 | Under Construction | 7 | 5 | 2 | Private | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
201702 |  | 2016-07-01 | GRAY STREET, 44 | DEANSCOURT LTD | 0.4596 | 2016-07-01 | Under Construction | 14 | 0 | 14 | Private | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
201813 | H16 | 2018-04-01 | MAXWELLTOWN, FORMER MULTIS | DUNDEE CITY COUNCIL | 0.61367 |  | Allocated in LDP | 30 | 0 | 30 | TBC | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 30
201814 | H34 | 2018-04-01 | ETIVE GARDENS, FORMER GOWRIEHILL PS | DUNDEE CITY COUNCIL | 1.6697 |  | Allocated in LDP | 35 | 0 | 35 | TBC | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
201815 | H35 | 2018-04-01 | DENOON TERRACE, FORMER HILLSIDE PS | DUNDEE CITY COUNCIL | 1.9738 |  | Allocated in LDP | 45 | 0 | 45 | Private | 0 | 0 | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
201816 | H36 | 2018-04-01 | HIGH STREET, LOCHEE, FORMER ST MARYS INFANT SCHOOL | DUNDEE CITY COUNCIL | 0.36187 |  | Allocated in LDP | 10 | 0 | 10 | RSL | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
201817 | H37 | 2018-04-01 | BURN STREET, FORMER BALDRAGON ACADEMY | DUNDEE CITY COUNCIL | 4.926 |  | Allocated in LDP | 70 | 0 | 70 | TBC | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 70
201825 | H14 | 2018-04-01 | GREENMARKET, FORMER RAILYARDS | SCOTTISH ENTERPRISE | 2.1768 |  | Allocated in LDP | 110 | 0 | 110 | TBC | 0 | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 110
201826A | H29 | 2017-10-16 | SUMMERFIELD GARDENS NORTH | INVERTAY HOMES | 2.1476 | 2017-10-16 | Under Construction | 40 | 1 | 3 | Private | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
201826C | H29 | 2022-06-13 | SUMMERFIELD AVENUE AT SUMMERFIELD GARDENS, LAND TO WEST | INVERTAY HOMES | 1.9422 | 2022-06-13 | Not Started | 34 | 0 | 34 | RSL | 0 | 0 | 15 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
201826D | H29 | 2023-03-30 | SUMMERFIELD AVENUE AT SUMMERFIELD GARDENS, LAND TO WEST | INVERTAY HOMES | 0.36088 | 2023-03-30 | Under Construction | 8 | 0 | 8 | Private | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
201827 | H33 | 2018-04-01 | DRUMGEITH ROAD, KELLYFIELD | DUNDEE CITY COUNCIL | 8.4241 |  | Allocated in LDP | 100 | 0 | 100 | TBC | 0 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | 0 | 100
201902 |  | 2018-07-16 | COLDSIDE ROAD, LAND SOUTH OF | CALEDONIA HA | 0.8538 | 2018-07-16 | Under Construction | 30 | 0 | 30 | RSL | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
201906 |  | 2018-09-25 | LANGLANDS STREET | HILLCREST HA | 0.14061 | 2018-09-25 | Under Construction | 16 | 0 | 16 | RSL | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
201908 |  | 2018-12-20 | THORTER LOAN/SOUTH VICTORIA DOCK ROAD | HILLCREST HA | 0.57493 | 2018-12-20 | Under Construction | 119 | 0 | 119 | RSL | 60 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119
201910 |  | 2018-12-14 | GUTHRIE STREET, THE OLD MILL | RAMSAY PROPERTIES LTD | 0.28532 | 2018-12-14 | Under Construction | 17 | 0 | 17 | Private | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
201912 |  | 2019-04-09 | ELLENGOWAN DRIVE | HILLCREST HA | 3.9484 | 2019-04-09 | Under Construction | 130 | 62 | 68 | RSL | 8 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68
201913 |  | 2018-06-21 | CANDLE LANE, 9-11 | HILLCREST HA | 0.18191 | 2018-06-21 | Under Construction | 24 | 0 | 24 | RSL | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
202002 |  | 2019-05-28 | LIFF HOSPITAL | MILLER HOMES | 6.4486 | 2019-05-28 | Under Construction | 54 | 8 | 1 | Private | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
202003 |  | 2019-04-17 | MURRAYGATE, 11-23 | HILLCREST HA | 0.068721 | 2019-04-17 | Under Construction | 31 | 0 | 31 | RSL | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
202009 |  | 2019-09-18 | MORGAN STREET, TAYBANK WORKS PH 2 | CALEDONIA HA | 0.91844 | 2021-11-19 | Detailed Planning Consent | 37 | 0 | 37 | RSL | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
202012 |  | 2019-12-18 | KINGSWAY EAST, FORMER STEWART HOUSE | PERSIMMON HOMES | 2.8817 | 2023-09-07 | Under Construction | 71 | 0 | 71 | Private | 13 | 36 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71
202013 |  | 2020-01-23 | BUTTARS LOAN, SITE TO THE EAST | GREEN PADS LTD | 0.21362 | 2020-01-23 | Under Construction | 8 | 0 | 8 | Private | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202022 |  | 2020-05-01 | EAST SCHOOL ROAD, DOWNFIELD HOUSE | ABERKELL DEVELOPMENTS | 0.31929 | 2020-05-01 | Under Construction | 14 | 6 | 8 | Private | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202024 |  | 2020-05-21 | PITKERRO ROAD, NORTH OF, LONGHAUGH ROAD, EAST OF | LONGHAUGH DEVELOPMENTS LTD | 1.02 | 2020-05-21 | Under Construction | 14 | 9 | 5 | Private | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
202030 |  | 2020-07-30 | GELLATLY STREET, 3 | MCGILL (DOCK STREET) LTD | 0.12902 | 2021-12-07 | Under Construction | 49 | 0 | 49 | Private | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
202041 |  | 2020-12-14 | CONSTABLE STREET, LOWER DENS WORKS, BLOCK G | STABLES DEVELOPMENT LLP | 0.083428 | 2020-12-14 | Detailed Planning Consent | 24 | 0 | 24 | Private | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
202051 |  | 2020-07-10 | PITKERRO ROAD, 114-116, LAND AT | ANGUS HA | 0.73952 | 2021-02-02 | Detailed Planning Consent | 21 | 0 | 21 | RSL | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
202053 |  | 2021-02-18 | MURRAYFIELD PLACE, MURRAYFIELD DRIVE, WHITFIELD AVENUE | DUNDEE CITY COUNCIL | 2.1982 | 2022-07-25 | Detailed Planning Consent | 42 | 0 | 42 | DCC | 0 | 0 | 22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
202055 |  | 2021-03-22 | TANNADICE STREET - 28-30, COURT STREET - 32 | ARB PROPERTIES | 0.035304 | 2021-03-22 | Detailed Planning Consent | 7 | 0 | 7 | Private | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
202065 |  | 2020-11-18 | DALKEITH ROAD, 57 | PRIVATE | 0.26635 | 2020-11-18 | Detailed Planning Consent | 8 | 0 | 8 | Private | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
202066 |  | 2020-12-17 | LIFF PLACE, BROWNHILL PLACE | BLACKWOOD HOMES & CARE | 0.65834 | 2020-12-17 | Under Construction | 23 | 0 | 23 | RSL | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
202067 |  | 2020-12-17 | GOURDIE PLACE, GOURDIE CRESCENT, LAND AT | BLACKWOOD HOMES & CARE | 0.91009 | 2020-12-17 | Under Construction | 22 | 0 | 22 | RSL | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
202068 |  | 2020-12-17 | BUTTARS ROAD, LAND TO SOUTH | BLACKWOOD HOMES & CARE | 0.48089 | 2020-12-17 | Under Construction | 9 | 0 | 9 | RSL | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
202071 |  | 2021-02-21 | SOAPWORK LANE, SOAPWORK LANE HOUSE | HILLCREST HA | 0.12926 | 2021-02-24 | Under Construction | 15 | 0 | 15 | RSL | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
202104 |  | 2021-06-16 | LAND AT FORMER ROSEBANK PRIMARY SCHOOL | DISCOVERY HOMES LTD | 1.3419 | 2021-06-16 | Under Construction | 40 | 0 | 40 | RSL | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
202106 |  | 2021-08-01 | COUPAR ANGUS ROAD, 40, SITE OF FORMER HOTEL | HILLCREST HA | 0.2112 | 2021-08-17 | Under Construction | 18 | 0 | 18 | RSL | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
202107 |  | 2021-12-01 | PERTH ROAD, 329, FERNBRAE HOSPITAL | S1 WEST LTD | 1.1481 | 2021-12-15 | Detailed Planning Consent | 22 | 0 | 22 | Private | 0 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
202108 |  | 2021-04-21 | LAND AT FORMER TAY ROPE WORKS MAGDALEN YARD ROAD | F & H DEVELOPMENTS | 0.25114 | 2021-04-21 | Under Construction | 9 | 0 | 9 | Private | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
202201 |  | 2022-02-09 | LAND TO EAST OF 247 BLACKNESS ROAD | DUNDEE CITY COUNCIL | 0.1765 | 2022-02-09 | Detailed Planning Consent | 24 | 0 | 24 | RSL | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
202202 |  | 2022-03-16 | SITE OF FORMER FACTORY BALLINDEAN ROAD | CULLROSS LTD/CALEDONIA HA/BOC LTD | 2.1002 | 2022-03-16 | Under Construction | 67 | 0 | 67 | Mixed | 12 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67
202203 |  | 2022-03-17 | NICOLL STREET, 6 | PRIVATE | 0.039053 | 2022-03-17 | Detailed Planning Consent | 10 | 0 | 10 | Private | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
202204 |  | 2022-02-17 | SITE OF FORMER JAMES KEILLER BUILDINGS 32 - 34 MAINS LOAN | BARRATT NORTH SCOTLAND/MARKETGAIT DEVELOPMENTS | 6.3067 | 2022-02-17 | Under Construction | 223 | 0 | 223 | Private | 0 | 53 | 50 | 50 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 223
202205 |  | 2022-03-17 | BURNSIDE STREET, 55 | HILLCREST HA | 0.57137 | 2022-03-17 | Detailed Planning Consent | 54 | 0 | 54 | RSL | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
202206 |  | 2021-05-21 | BROWNHILL PLACE, BROWNHILL STREET | BLACKWOOD HOMES & CARE | 0.29665 | 2021-05-21 | Under Construction | 12 | 0 | 12 | RSL | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
202207 |  | 2019-01-21 | BUCHANAN STREET, ELECTRIC SUB-STATION | PRIVATE | 0.118 | 2022-04-21 | Detailed Planning Consent | 14 | 0 | 14 | Private | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
202303 |  | 2022-09-27 | GUTHRIE STREET, 9 | PRIVATE | 0.15991 | 2022-09-27 | Detailed Planning Consent | 18 | 0 | 18 | Private | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
202308 |  | 2022-12-22 | ELLIOT ROAD, MAINS OF BALGAY | PRIVATE | 0.30628 | 2022-12-22 | Detailed Planning Consent | 5 | 0 | 5 | Private | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
202309 |  | 2022-12-22 | 114 HILLTOWN, MOSQUE | PRIVATE | 0.22 | 2022-12-22 | Detailed Planning Consent | 5 | 0 | 5 | Private | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
202310 |  | 2023-02-10 | CANDLE LANE, 3-7 | MURRAYFIELD PROPERTIES LTD | 0.044777 | 2023-02-10 | Detailed Planning Consent | 8 | 0 | 8 | Private | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Totals | [7 empty] | 3210 | 181 | 2848 |  | 558 | 411 | 497 | 487 | 360 | 199 | 120 | 70 | 70 | 76 | 0 | 2848

## Constrained - Brownfield
Constrained Brownfield 2022/23
HLA Ref | LDP 2019 Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Type | Site Status | Site Capacity | Complete 22/23 | Total Completions | Units to build | TenureType | Owner / Developer | Reason Constrained
200321 | H13 | 2003-04-01 | QUEEN VICTORIA WORKS | 1.2498 |  | CON | Allocated in LDP | 50 | 0 | 0 | 50 | Private | PRIVATE | OWNERSHIP
201205 | H02 | 2012-04-01 | EARN CRESCENT, LAND AT | 0.56489 |  | CON | Allocated in LDP | 20 | 0 | 0 | 20 | Private | DUNDEE CITY COUNCIL | LAND USE
200728 | H18 | 2007-04-01 | PRINCES STREET | 0.25972 |  | CON | Allocated in LDP | 20 | 0 | 0 | 20 | Private | DUNDEE CITY COUNCIL | LAND USE
200353 | H26 | 2003-04-01 | LOTHIAN CRESCENT | 0.83453 |  | CON | Allocated in LDP | 15 | 0 | 0 | 15 | RSL | DUNDEE CITY COUNCIL | LAND USE
201220 | H19 | 2012-04-01 | BARNS OF CLAVERHOUSE ROAD, MOM PHASE 4 | 0.41142 |  | CON | Allocated in LDP | 12 | 0 | 0 | 12 | Private | DUNDEE CITY COUNCIL | LAND USE
200807 | H04 | 2008-04-01 | QUARRY GARDENS | 0.44319 |  | CON | Allocated in LDP | 18 | 0 | 0 | 0 | Private | DUNDEE CITY COUNCIL | PHYSICAL
200723 |  | 2007-04-01 | WALLACE CRAIGIE WORKS | 1.6829 | 2012-10-23 | CON |  | 100 | 0 | 0 | 147 | Private | UNICORN PROPERTIES | PHYSICAL

## Constrained - Greenfield 22-23
Constrained Greenfield 2022/23
HLA Ref | LDP 2019 Ref | Date Added | Site | Owner / Developer | Site Area (ha) | Last Approval Date | Site Type | Site Status | Date Expired | Site Capacity | Complete 22/23 | Total Completions | Units to build | Greenfield/ Brownfield | Windfall site | Tenure Type | Reason Constrained
201509 |  | 2015-04-01 | LINLATHEN HOUSE, LAND TO EAST OF | PRIVATE | 1.5242 |  | CON |  |  | 60 | 0 | 0 | 60 | Greenfield | Y | Private | LANDUSE
201424 | H47 | 2014-04-01 | STRATHYRE AVENUE, LAND TO EAST OF | PRIVATE | 1.5713 |  | CON | Allocated in LDP |  | 26 | 0 | 0 | 26 | Greenfield | N | Private | OWNERSHIP

## Small Sites 22-23
Small Sites 2022/23
Audit Year 13/14
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
201410A | 2013-12-13 | WEST GROVE AVENUE,10 | 0.13055 | 2022-03-04 | Under Construction | 1 | 1
Audit Year 14/15
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
201607L | 2015-05-15 | COLLINGWOOD CRESCENT, 20, LAND TO WEST OF | 0.040366 | 2019-05-01 | Under Construction | 1 | 1
Audit Year 16/17
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
201705G | 2016-06-24 | DUDHOPE TERRACE, 7 | 0.14695 | 2019-12-19 | Not Started | 1 | 1
201705H | 2016-09-14 | MONIFIETH ROAD, 96 | 0.057013 | 2016-09-14 | Under Construction | 1 | 1
201705K | 2016-12-08 | DUNDEE ROAD, HOLLY HILL, 69 | 0.18299 | 2022-11-24 | Not Started | 1 | 1
201410C | 2017-01-05 | BUGHTIES ROAD, 22 | 0.086026 | 2020-01-13 | Under Construction | 1 | 1
Audit Year 17/18
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
201805B | 2017-05-12 | MONIFIETH ROAD, 92A | 0.11064 | 2017-05-12 | Under Construction | 2 | 2
201805C | 2017-05-24 | GLAMIS ROAD, 28A | 0.040016 | 2021-08-19 | Not Started | 1 | 1
201805D | 2017-06-01 | HAREFIELD ROAD, 16, LAND TO EAST OF | 0.15268 | 2022-03-10 | Not Started | 1 | 1
201805G | 2017-10-26 | GIBSON TERRACE, 3, LAND EAST OF | 0.13844 | 2020-08-28 | Not Started | 1 | 1
201805J | 2017-11-15 | PRINCES STREET, 161 | 0.038506 | 2017-11-15 | Under Construction | 3 | 3
201805M | 2018-03-26 | ARBROATH ROAD, NORTH GRANGE FARM | 0.18637 | 2021-05-07 | Not Started | 1 | 1
Audit Year 18/19
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
201904A | 2018-05-07 | PERTH ROAD, 474, LAND TO EAST OF COACH HOUSE | 0.13366 | 2021-05-07 | Under Construction | 1 | 1
201904F | 2018-09-06 | ALBERT SQUARE, 21 | 0.021746 | 2018-09-06 | Under Construction | 2 | 2
201904G | 2018-10-15 | RIVER CRESCENT, GARDEN GROUND WEST OF BURNSIDE | 0.068992 | 2020-04-30 | Under Construction | 1 | 1
Audit Year 20/21
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
202004L | 2019-10-25 | PITKERRO MILL | 0.21775 | 2019-10-25 | Under Construction | 2 | 2
202004P | 2020-01-31 | ROCKFIELD CRESCENT, 7, LAND TO NORTH | 0.11705 | 2020-01-31 | Not Started | 1 | 1
Audit Year 20/21
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
202019C | 2020-05-20 | DOUGLAS TERRACE, 12 | 0.027588 | 2020-05-20 | Under Construction | 1 | 1
202019D | 2020-05-26 | MONIFIETH ROAD, 69, STONELEE GUEST HOUSE | 0.021311 | 2020-05-26 | Under Construction | 1 | 1
202019E | 2020-06-25 | VICTORIA ROAD, 1, BROUGHTY FERRY | 0.96804 | 2020-06-25 | Not Started | 3 | 3
202019F | 2020-06-25 | ALBANY ROAD, 39A | 0.11537 | 2020-06-25 | Under Construction | 2 | 2
202031 | 2020-07-31 | PITKERRO MILL | 0.21123 | 2020-07-31 | Not Started | 2 | 2
202032A | 2020-07-31 | SYMERS STREET, LAND TO EAST OF 6 | 0.025906 | 2020-07-31 | Not Started | 1 | 1
202061D | 2020-08-11 | NETHERGATE, 138, BASEMENT | 0.012799 | 2020-08-11 | Under Construction | 1 | 1
202035B | 2020-08-31 | ERSKINE STREET, 20 | 0.0095214 | 2020-08-31 | Not Started | 1 | 1
202032B | 2020-09-01 | FAIRFIELD ROAD, 10 | 0.20792 | 2021-11-11 | Under Construction | 4 | 4
202032C | 2020-09-02 | FAIRFIELD ROAD, 10 | 0.20667 | 2022-07-29 | Under Construction | 2 | 1
202035A | 2020-09-04 | ADELAIDE PLACE, BOWLING GREEN, LAND TO WEST | 0.053539 | 2020-09-04 | Not Started | 1 | 1
202035C | 2020-10-02 | ALBANY ROAD, 50, GARDEN GROUND TO SOUTH | 0.28591 | 2020-10-02 | Not Started | 1 | 1
202061B | 2020-10-22 | DALKEITH ROAD, 69 | 0.22415 | 2020-10-22 | Under Construction | 4 | 4
202043 | 2020-11-06 | BROWN STREET, 75/77, BROUGHTY FERRY | 0.012892 | 2022-11-18 | Not Started | 2 | 2
202035D | 2020-11-10 | SPRINGHILL, 13 | 0.047011 | 2020-11-10 | Not Started | 1 | 1
202035F | 2020-11-12 | DUDHOPE TERRACE, 9 | 0.13097 | 2020-11-12 | Under Construction | 1 | 1
202035G | 2020-11-26 | VICTORIA ROAD, 10,G1 VICTORIA CHAMBERS | 0.010618 | 2020-11-26 | Under Construction | 1 | 1
202035H | 2020-12-11 | MURRAYGATE, 39, 1/0 | 0.018125 | 2020-12-11 | Under Construction | 3 | 3
202035I | 2021-01-06 | HILLTOWN, 245 | 0.012996 | 2021-01-06 | Not Started | 1 | 1
202035J | 2021-01-13 | COMMERCIAL STREET, 84, 2/1 | 0.025383 | 2021-01-13 | Not Started | 1 | 1
202035K | 2021-02-10 | CAENLOCHAN ROAD, 4 | 0.11504 | 2021-02-10 | Not Started | 1 | 1
202061G | 2021-02-23 | DYKES OF GRAY, BRAESIDE | 0.4224 | 2021-02-23 | Under Construction | 1 | 1
202035L | 2021-03-09 | WEST BELL STREET, 1A | 0.080352 | 2021-03-09 | Not Started | 3 | 3
Audit Year 21/22
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
202061H | 2021-04-21 | NORTH GRANGE FARM, LAND TO EAST OF FARMHOUSE | 0.078398 | 2021-04-12 | Under Construction | 1 | 1
202061F | 2021-05-12 | AMERICANMUIR ROAD, 38, GARDEN GROUND | 0.13032 | 2021-05-12 | Detailed Planning Consent | 1 | 1
202105B | 2021-07-01 | SPRINGFIELD, 8, G/0 | 0.022691 | 2021-07-16 | Not Started | 2 | 2
202105C | 2021-08-01 | FREDERICK STREET, 45, GARDEN GROUND | 0.072435 | 2023-02-08 | Not Started | 1 | 1
202105I | 2021-08-01 | STRATHERN ROAD, 140 | 0.11464 | 2021-08-20 | Not Started | 1 | 1
202105J | 2021-08-01 | BALGOWAN DRIVE, 7 | 0.056125 | 2021-08-17 | Detailed Planning Consent | 1 | 1
202105K | 2021-08-01 | SOUTH TAY STREET, 28, GROUND & BASEMENT | 0.01514 | 2021-08-26 | Under Construction | 2 | 2
202105G | 2021-08-21 | REFORM STREET, 51, 2/2, CAFE | 0.010331 | 2021-08-27 | Detailed Planning Consent | 1 | 1
202105D | 2021-10-01 | NORTH STREET, 40 | 0.021458 | 2021-10-21 | Not Started | 1 | 1
202105F | 2021-11-01 | REFORM STREET, 51, MF SPACE | 0.010331 | 2021-11-18 | Detailed Planning Consent | 4 | 4
202105H | 2021-12-01 | SOUTHAMPTON ROAD, FORMER CRAIGIE HOUSE, LAND AT | 0.34849 | 2021-12-14 | Detailed Planning Consent | 1 | 1
202208 | 2022-03-16 | FORTHILL ROAD, 10 | 0.041527 | 2022-03-16 | Not Started | 1 | 1
Audit Year 22/23
HLA Ref | Date Added | Site | Site Area (ha) | Last Approval Date | Site Status | Site Capacity | Units to build
202302 | 2022-08-23 | ELLISLEA ROAD, 9, GARDEN GROUND | 0.10892 | 2022-08-23 | Detailed Planning Consent | 1 | 1
202304 | 2022-11-10 | CAMPHILL ROAD, 65, LAND TO SOUTH | 0.17794 | 2022-11-10 | Detailed Planning Consent | 1 | 1
202305 | 2022-11-23 | BALGILLO ROAD, 157, LAND SOUTH | 0.10384 | 2022-11-23 | Detailed Planning Consent | 1 | 1
202306 | 2022-11-25 | LAUDERDALE AVENUE, 88, GARDEN GROUND TO SOUTH | 0.03012 | 2022-11-25 | Not Started | 1 | 1
202311 | 2023-03-08 | LOCHEE ROAD, 142A | 0.020025 | 2023-03-08 | Detailed Planning Consent | 1 | 1
202313 | 2023-03-31 | DYKES OF GRAY ROAD, SOUTH OF MAINS OF GRAY FARM | 0.28448 | 2023-03-31 | Detailed Planning Consent | 1 | 1
202314 | 2023-06-22 | BROOK STREET, 197, 2/2, BROUGHTY FERRY | 0.033857 | 2022-06-02 | Not Started | 1 | 1

## Completed Sites - All
Completed Sites
HLA Ref | LDP 2019 Ref | Date Added | Site | Owner/ Developer | Site Area (ha) | Last Approval | Site Status | Date Site Completed | Site Capacity | Complete 22/23 | Total Complete | Greenfield / Brownfield | Tenure Type
200504C | H32 | 2020-01-30 | ABERLADY CRESCENT PHASE 3A | DJ LAING | 0.64617 | 2020-01-30 | Site Complete | 2022-04-04 | 10 | 1 | 10 | Brownfield | Private
200739 |  | 2007-04-01 | WHITFIELD LATER PHASES | MERCHANT/HOME SCOTLAND | 1.88 | 20/06/2014 | Site Complete | 30/09/2022 | 49 | 9 | 49 | Brownfield | RSL
201009B | H30 | 2018-11-15 | HADDINGTON AVENUE (Phase 2) | MERCHANT/HOME SCOTLAND | 1.7442 | 2019-09-19 | Site Complete | 2022-10-25 | 27 | 27 | 27 | Brownfield | Private/RSL
201422 |  | 2014-04-01 | FINAVON STREET, LAND EAST OF | ABERTAY HA | 2.9652 | 2016-10-28 | Site Complete | 2022-05-03 | 56 | 5 | 56 | Brownfield | RSL
201604 |  | 2015-05-07 | NORTH ISLA STREET, 4 | CITY BLINDS | 0.065419 | 2015-05-07 | Site Complete | 2022-10-07 | 8 | 1 | 8 | Brownfield | Private
201605 |  | 2015-11-09 | EAST DOCK STREET, 26 | PRIVATE | 0.056666 | 2015-11-09 | Site Complete | 2022-04-08 | 10 | 1 | 10 | Brownfield | Private
201710 |  | 2017-03-10 | HEBRIDES DRIVE, LAND NORTH OF | PANMURE DEVELOPMENTS LTD | 0.6673 | 2018-04-25 | Site Complete | 2022-10-20 | 12 | 12 | 12 | Brownfield | Private
201802 |  | 2017-08-11 | OLD QUARRY ROAD, BALLUMBIE LAND NORTH OF | KNOWE PROPERTIES LTD | 1.0315 | 2017-08-11 | Site Complete | 2023-02-21 | 12 | 1 | 12 | Brownfield | Private
201819 | H39 | 2018-04-01 | LONGHAUGH ROAD, FORMER ST LUKES & ST MATTTHEWS PS | ANGUS HA | 2.0412 | 2020-03-06 | Site Complete | 2023-02-21 | 40 | 40 | 40 | Brownfield | RSL
201820 | H40 | 2018-04-01 | FINTRY TERRACE, FORMER LONGHAUGH PS | ANGUS HA | 1.3046 | 2020-03-17 | Site Complete | 2023-01-20 | 32 | 32 | 32 | Brownfield | RSL
201824A | H45 | 2019-09-25 | BALLUMBIE ROAD, LAND TO EAST OF - PHASE 1 | STEWART MILNE | 3.7672 | 2019-09-25 | Site Complete | 2022-09-08 | 76 | 12 | 76 | Greenfield | Private
201826B | H29 | 2020-10-01 | DRUMGEITH ROAD/STRATHAVEN TERRACE | MERCHANT | 0.7816 | 2020-10-29 | Site Complete | 2023-02-02 | 12 | 12 | 12 | Brownfield | Private
201904I |  | 2018-12-07 | HILL STREET, 24 | PRIVATE | 0.29866 | 2018-12-07 | Site Complete | 2023-03-15 | 1 | 1 | 1 | Brownfield | Private
202004B |  | 2019-07-05 | DRUMSTURDY ROAD, NO 1 HOLDING | PRIVATE | 0.058381 | 2019-07-05 | Site Complete | 2023-01-24 | 1 | 1 | 1 | Brownfield | Private
202004K |  | 2019-09-12 | UNION TERRACE, 10 | PRIVATE | 0.043638 | 2019-09-12 | Site Complete | 2022-10-17 | 1 | 1 | 1 | Brownfield | Private
202005 |  | 2019-05-06 | COMMERCIAL STREET, 23 | AKG PROPERTY GROUP | 0.01573 | 2019-05-06 | Site Complete | 2022-05-12 | 7 | 7 | 7 | Brownfield | Private
202018 |  | 2018-03-21 | FORMER KINGSPARK SCHOOL | PERSIMMON HOMES | 2.8754 | 2018-03-21 | Site Complete | 2022-12-02 | 62 | 30 | 62 | Brownfield | Private
202056 |  | 2020-08-21 | DALMAHOY DRIVE, LAND TO WEST | KIRKWOOD HOMES | 4.1087 | 2020-12-16 | Site Complete | 2023-02-07 | 49 | 6 | 49 | Greenfield | Private
202061E |  | 2021-04-21 | FAIRFIELD ROAD, 29, GARDEN GROUND TO REAR | PRIVATE | 0.062862 | 2021-04-21 | Site Complete | 2023-03-13 | 1 | 1 | 1 | Brownfield | Private
202105A |  | 2021-07-01 | LAMMERTON TERRACE, GARDEN GROUND NORTH OF 3A | PRIVATE | 0.039409 | 2021-07-05 | Site Complete | 2022-10-26 | 1 | 1 | 1 | Brownfield | Private
202109 |  | 2021-11-19 | GARRY TERRACE, 17 - 21 | SIDLAW BUILDING & JOINERY SERVICES | 0.22927 | 2021-11-19 | Site Complete | 2023-03-15 | 9 | 9 | 9 | Brownfield | Private

## Expired Sites - All
Expired Sites
HLA Ref | LDP 2019 Ref | Date Added | Site | Owner / Developer | Site Area (ha) | Last Approval Date | Site Status | Date Expired | Site Capacity | Greenfield/ Brownfield | Tenure Type
201805L |  | 2018-02-21 | GOTTERSTONE DRIVE, 61 | PRIVATE | 0.035516 | 2018-02-21 | Consent Expired | 2023-02-21 | 1 | Brownfield | Private
201911 |  | 2020-01-31 | DICKSON AVENUE, THE ROCK | ROCK DEVELOPMENTS (SCOTLAND) LTD | 0.15234 | 2020-01-31 | Consent Expired | 2023-01-31 | 11 | Brownfield | Private
202014 |  | 2020-01-31 | DYKES OF GRAY ROAD, HOUSE OF GRAY | PRIVATE | 1.4013 | 2020-01-31 | Consent Expired | 2023-01-31 | 10 | Brownfield | Private
202004N |  | 2019-12-20 | WEST BELL STREET, 3-5, BASEMENT | PRIVATE | 0.016493 | 2019-12-20 | Consent Expired | 2022-12-20 | 4 | Brownfield | Private
202011 |  | 2019-11-27 | SEAGATE, 36-40 | DISCOVERY HOMES LTD | 0.084292 | 2019-11-27 | Consent Expired | 2022-11-27 | 27 | Brownfield | Private
201607D |  | 2016-03-04 | GRAY STREET, 21 | TAYBANK PROPERTIES LTD | 0.033121 | 2019-11-21 | Consent Expired | 2022-11-21 | 1 | Brownfield | Private
201410B |  | 2013-10-01 | MARGARET CRESCENT, 4 | PRIVATE | 0.071456 | 2019-11-04 | Consent Expired | 2022-11-04 | 1 | Brownfield | Private
202004D |  | 2019-08-02 | ANCRUM ROAD, 21 | PRIVATE | 0.041956 | 2019-08-02 | Consent Expired | 2022-08-02 | 1 | Brownfield | Private
202008 |  | 2019-07-25 | WEST MARKETGAIT | MARKETGAIT DUNDEE LTD | 0.134 | 2022-12-13 | Consent Expired | 2022-07-25 | 43 | Brownfield | Private
201904E |  | 2018-06-11 | QUEEN STREET, 89, BRAE COTTAGE | PRIVATE | 0.10459 | 2019-06-21 | Consent Expired | 2022-06-21 | 4 | Brownfield | Private
202004C |  | 2019-06-21 | HIGH MILL COURT, BASEMENT, UNIT 2 | PRIVATE | 0.028243 | 2019-06-21 | Consent Expired | 2022-06-21 | 2 | Brownfield | Private
202007 |  | 2019-06-18 | TRADES LANE, 28 | A B ROGER & YOUNG LTD | 0.080693 | 2019-06-18 | Consent Expired | 2022-06-18 | 28 | Brownfield | Private
202006 | . | 2006-12-05 | PERTH ROAD, FORMER BLACKNESS NURSERY | PRIVATE | 1.1232 | 2019-06-05 | Consent Expired | 2022-06-05 | 10 | Brownfield | Private
202004G |  | 2019-05-31 | CASTLE CHAMBERS, 26 CASTLE STREET | PRIVATE | 0.010686 | 2019-05-31 | Consent Expired | 2022-05-31 | 2 | Brownfield | Private
201705B |  | 2010-04-08 | BROOK STREET, 197, 2/2, BROUGHTY FERRY | PRIVATE | 0.033857 | 2022-06-02 | Consent Expired | 2022-05-10 | 1 | Brownfield | Private
202004E |  | 2019-04-11 | WHITEHALL CRESCENT, 7, 2nd Floor | PRIVATE | 0.012002 | 2019-04-11 | Consent Expired | 2022-04-11 | 1 | Brownfield | Private
202004F |  | 2019-04-11 | WHITEHALL CRESCENT, 7, 1st Floor | PRIVATE | 0.012002 | 2019-04-11 | Consent Expired | 2022-04-11 | 1 | Brownfield | Private